## Hungary
Phase	Item	Start Date	End Date	Status	Owner	Comment
Dev3 pre-patch	Quick sanity on dev3			NA	Rukayya/Roqaiya

	Check PI tool			NA	Chris

	Run UUID script			NA	Chris

	Keep full backup of dev3 for restoration purpose			NA	Chris

	Clone dev6 and dev7 environments from dev3 (use dev6 env for upgrade and dev7 env for comparison)			Done	Chris

Dev6 upgrade	Change Jenkins tag to 2.8.2	13-Dec	13-Dec	Done	Chris

	Run UUID script	13-Dec	13-Dec	Done	Chris	No duplicacy (PASS)

	Check PI tool and create a PR	13-Dec	13-Dec	In progress	Chris	PI status shows fail (have to raise deviation request)

	Regression testing on dev6 and note all issues	14-Dec	14-Dec	Done	Rukayya/Roqaiya	Issues found

Dev3 upgrade(only if dev6 is clean)	Change Jenkins tag to 2.8.2				Chris

	Run UUID script				Chris

	Check PI tool and create a PR				Chris

	Regression testing on dev3 and note all issues (compare it with dev7)				Rukayya/Roqaiya

## Belgium
Phase	Item	Start Date	End Date	Status	Owner	Comment
Dev3 pre-patch	Quick sanity on dev3	14-Dec	14-Dec	Done	Rukayya/Roqaiya

	Check PI tool	13-Dec	13-Dec	Done	Chris	PI status fail

	Run UUID script	13-Dec	13-Dec	Done	Chris	Contains duplicate UUID's

	Keep full backup of dev3 for restoration purpose	13-Dec	13-Dec	Done	Chris

	Clone dev6 and dev7 environments from dev3 (use dev6 env for upgrade and dev7 env for comparison)	14-Dec	14-Dec	Done	Chris

Dev6 upgrade	Change Jenkins tag to 2.8.2	14-Dec	14-Dec	Done	Chris

	Run UUID script	14-Dec	14-Dec	Done	Chris	No duplicacy (PASS)

	Check PI tool and create a PR	14-Dec	14-Dec	Done	Chris	PI status shows fail (have to raise deviation request)

	Regression testing on dev6 and note all issues	15-Dec	15-Dec	Done	Rukayya/Roqaiya	Issues found

Dev3 upgrade(only if dev6 is clean)	Change Jenkins tag to 2.8.2				Chris

	Run UUID script				Chris

	Check PI tool and create a PR				Chris

	Regression testing on dev3 and note all issues (compare it with dev7)				Rukayya/Roqaiya