## Summary
Month | Launch | Market Setup | Over Capacity | Resource | Argentina | China | Ireland | Malyasia | Brazil | Costa rica | Romania | Venezuela | Austria | Gulf Levant | Mexico | Poland | Australia | Canada | Saudi Arabia | Taiwan | Poland | Sweden | Switzerland | Israil | New Zea | Czech Rep | Egypt | Italy | Turkey | France | Russia | Spain | Hungry | Belgium | Greece | Portugal | Norway | Netherlands | Finland | Ireland | Romania | Asutria | Switzerland
Market Type
April 16
May 16
June 16
July 16 | 5 | 3
Aug 16 | 4 | 7 | [14 empty] | 2.6
Sep 16 | 4 | 7 |  | 2QA + 1D | [8 empty] | 2.6 | [22 empty] | 8-13 Sep | 16- 19 Sep | 14- 20 Sep
Oct 16 | 8 | 3 |  | 4QA + 2D
Nov 16 | 7 | 3 |  | 4QA + 2D | [8 empty] | 2.7
Dec 16 | 1 | 1 |  | 1QA + 1D | [8 empty] | 2.7
Jan 17 | 2 | 0 |  | 2D
Feb 17 | 3 | 0 |  | 2QA + 1D
Go-Live
UAT and Market Setup
Deviation in Plan

## Resource Matrix
Month | Market | Type | Activity | Start | End | Resource | Name | Status
September | Austria | 2.3 - 2.6 | Launch | 2016-09-01 | 2016-09-14 | R1 | Ghanendra | Done
| Mexico | 2.3 - 2.6 | Launch | 2016-08-23 | 2016-09-07 | R2 | Rachit | Done
| Poland | New 2.7 | Launch | 2016-09-14 | 2016-09-29 | R1 | Chris | Pending
| Italy | 2.6 - 2.7 | Launch | 2016-09-19 | 2016-10-05 | R2 | Rachit | Pending
| France | 2.6 - 2.7 | Rollout | 2016-09-07 | 2016-09-19 | R2 | Ghanendra | Pending
| Russia | 2.6 - 2.7 | Rollout | 2016-09-19 | 2016-09-23 | R3 | Roquiya/Sayed | Pending
| Hungary | New 2.7 | Rollout | 2016-09-01 | 2016-09-06 | R3 | Nikhil | Pending
| Belgium | New 2.7 | Rollout | 2016-09-15 | 2016-09-19 | R4 | Nikhil | Pending
| Portugal | 2.6 - 2.7 | Rollout | 2016-09-08 | 2016-09-19 | R5 | Chris | Pending
| Norway | 2.6 - 2.7 | Rollout | 2016-09-16 | 2016-09-22 | R5 | Ghanendra | Pending
| Netherlands | 2.6 - 2.7 | Rollout | 2016-09-20 | 2016-09-22 | R4 | Ghanendra | Pending
| Switzerland | New 2.7 | Rollout | 2016-09-23 | 2016-09-30 | R6 | Ghanendra | NA
Oct | Australia | 2.3 - 2.6 | Launch | 2016-10-13 | 2016-10-27 | R1
| Saudi Arabia | 2.3 - 2.6 | Launch | 2016-10-01 | 2016-10-19 | R1
| Taiwan | 2.3 - 2.6 | Launch | 2016-09-26 | 2016-10-10 | R1
| France | 2.6 - 2.7 | Launch | 2016-09-20 | 2016-10-10 | R2
| Russia | 2.6 - 2.7 | Launch | 2016-10-01 | 2016-10-24 | R2
| Spain | 2.6 - 2.7 | Launch | 2016-10-17 | 2016-10-24 | R3
| Portugal | 2.6 - 2.7 | Launch | 2016-09-15 | 2016-10-05 | R3
| Norway | 2.6 - 2.7 | Launch | 2016-09-25 | 2016-10-17 | R6
| Netherlands | 2.6 - 2.7 | Launch | 2016-09-15 | 2016-10-11 | R4
| Finland | 2.6 - 2.7 | Rollout | 2016-10-25 | 2016-11-10 | R4
| Ireland | 2.6 - 2.7 | Rollout | 2016-10-05 | 2016-10-13 | R5
Nov | Austria 2.7 |  | Rollout | 2016-11-21 | 2016-12-02 | R3
| Canada |  | Launch | 2016-11-07 | 2016-11-28 | R4
| Sweden |  | Launch | 2016-10-21 | 2016-11-10 | R1
| New Zealand |  | Rollout | 2016-11-08 | 2016-11-14 | R1
| Czech |  | Rollout | 2016-11-21 | 2016-11-28 | R3
| Spain |  | Launch | 2016-11-01 | 2016-11-21 | R4
| Belgium |  | Launch | 2016-11-07 | 2016-11-22 | R3
| Greece |  | Launch | 2016-11-07 | 2016-11-22 | R2
| Finland |  | Launch | 2016-10-15 | 2016-11-02 | R2
| Hungary |  | Launch | 2016-10-21 | 2016-11-10 | R3
| Israil |  | Launch | 2016-11-14 | 2016-12-01 | R1
Dec | Austria |  | Launch | 2016-12-01 | 2016-12-22 | R1
| Israil |  | Launch | 2016-11-14 | 2016-12-01 | R1
| Egypt |  | Rollout | 2016-12-06 | 2016-12-12 | R2
| Hungary |  | Launch | 2016-11-25 | 2016-12-11 | R2
2017-01-17 | Romania |  | Launch | 2017-01-01 | 2017-01-20 | R1
| Switzerland |  | Launch | 2017-01-01 | 2017-01-22 | R2
| Czech |  | Launch | 2017-01-13 | 2017-02-01 | R1
2017-02-01 | New Zealand |  | Launch | 2017-02-10 | 2017-02-27 | R1
| Czech |  | Launch | 2017-01-13 | 2017-02-01 | R1

## Slot Based Approach
Month | Upgrade Slot | Market Setup and Rollout |  | Go-Live
|  | W1 | W2 | W3 | W4 | Extras | Type
2016-09-01 | Slot 1 | France |  | Austria
| Slot 2 | Hungary |  | Mexico
| Slot 3 | Portugal |  | Poland
|  | Norway |  | Italy
Netherlands
2016-10-01 | Slot 1 |  |  | Australia
| Slot 2 |  |  | Saudi Arabia
Slot 3
2016-11-01 | Slot 1
Slot 2
Slot 3
2016-12-01 | Slot 1
Slot 2
Slot 3
2017-01-01 | Slot 1
Slot 2
Slot 3
2017-02-01 | Slot 1
Slot 2
Slot 3

## Go-Live Effort
Activity | ETA (Days) | Dependency | Owner
Go-Live heads up | 0 |  | Upgrade Team
Request to block the deployment slot | 0 |  | HCP Support
Request to procure domain name | 0 | SLA is 10 days | HCP Support
Request to procure and configure SSL | 0 | SLA is 10 days | HCP Support
Dev3 Checkpoints | 1 |  | HCP Support
Dev3 to stage move | 1 |  | HCP Support
Stage sanity test | 1 |  | HCP Support
Stage release for health check | 0 | On Market / Content team | HCP Support
Omniture verification | 0 | SLA is 5 days | HCP Support
Security approval on FOD Scan | 0 | SLA is 5 days | HCP Support
Go-Live checklist verification | 3 |  | HCP Support
MTP | 1 |  | Deployment team
Total Effort | 7
Please Note
Minimum 10 days heads up required if market is going live for first time
Minimum 6 days heads up is required if the market is already live

## Env Cloning Effort
Activity | ETA (days) | Dependency | Details | Owner
KT Checklist | 1 |  | Verification of all assets and information during transition to support. | HCP Support
UAT | 4 |  | 4 Days timeline to cover all test cases | HCP Support
UAT Fixes | 2 |  | Issues reported during UAT to be fixed by deployment team and reverification of the same by support | Deployment Team
UAT Signoff | 0 |  | Signoff on environment before environment cloning process starts | HCP Support
Request for DB Dump | 0 | 3 | HCP Support have to depend on global support to move the files after environment cloning is complete. Standard SLA of global support is 3 days. | Global Suppport
Cloning Environments | 3 |  | Replicating all dev environments and seeting up self service and other users. | HCP Support
Request to move the files | 0 | 3 | HCP Support have to depend on global support to move the files after environment cloning is complete. Standard SLA of global support is 3 days. | Global Support
Sanity test | 1 |  |  | HCP Support
Environment Release | 0 |  |  | HCP Support
Total ETA | 11
Please Note
Total turnaround time for UAT and Environment cloning activity is 16 days

## 2.6 Upgrade Calendar
Country | Upgrade Version | Status | Zendesk | JIRA Epic | Dev5 Handover | Upgrade Start | UAT and KT |  | Signoff date | Warrenty Ends | Env Clone Start | Env handover | Go-Live Activity Start | Launch | Comment | Dev Envs | [8 empty] | Tested Self Service (Dev -> Dev2) | Tested Self Service (Dev3 -> stage) | Tested Self Service (stage -> Prod | Owner
[7 empty] | Start Date | End Date | [7 empty] | Dev | Dev2 | Dev3 | Dev4 | Dev6 | Dev7 | Dev 8 | Stg | Stg2
[16 empty] | Status | Status | Status | Status | Status | Status | Status | Status | Status
Argentina | 2.3 - 2.6 | Soft Launch | 58861 | MD-930 | Done | 2015-12-23 | 2016-04-19 | 2016-04-25 | 2016-05-03 | 17th May | NA | NA | NA | 2016-07-07 |  | 7.x-2.8.x-BARIUM-dev | 2.6.8 | 2.6.9 | 2.6.7 | 2.6.8 | 2.6.8 | 2.6.8 | 7.x-2.8.x-BARIUM-dev |  |  |  |  | Pradeep
Australia | 2.3 - 2.6 | Build | 67061 | MD-1124 | MLR | 2015-06-09 | 2016-08-08 | 2016-08-10 | 16th Aug | 29th Aug | 16th Aug | 22nd Aug | 13th Oct | 2016-10-27 | [6 empty] | Pending | Pending | [5 empty] | NA
Austria | 2.3 - 2.6 | MTP | 51376 | MD-1441 | Done | 2016-03-18 | 2016-06-20 | 2016-06-28 | 28th June | 12th July | 28th June | 30th June | 2016-09-01 | 2016-09-14 | [5 empty] | Pending | Pending | Pending | [5 empty] | Eitisha
Brazil | 2.3 - 2.6 | MTP | 64434 | MD-926 | Done | 2016-05-24 | 2016-07-18 | 2016-07-22 | 25th July | 7th Aug | 25th July | 29th July | 10th Aug | 2016-08-24 |  | Pending | Pending | Pending | Done | Done | Pending | Done | Done |  |  |  |  | Ghanendra
Canada | New 2.6 | QA | NA | MD-879 | QA | 2015-09-28 | 2016-08-18 | 2016-08-22 | 2016-08-24 | 7th Sep | 2016-08-25 | 2016-08-31 | 7th Non | 2016-11-28 |  | Pending |  | Done | Pending | Pending | Pending | Pending |  |  | NA |  |  | NA
China | 2.1 - 2.6 | MTP | 61408 | MD-880 | Done | 2016-01-26 | 2016-04-12 | 2016-04-15 | 28th April | 12th May | NA | NA | NA | 2016-07-12 |  | Done | Done | Done | Done | Pending | Pending | Pending | [5 empty] | Eitisha
Costa rica | New 2.6 | MTP |  | MD-1375 | Done | 2016-02-26 | 2016-06-20 | 2016-06-28 | 12th July | 26th July | NA | NA | 3rd Aug | 2016-08-16 | Harshil | [12 empty] | Ashna
Finland | New 2.6 | Soft Launch | 40824 | MD-980 | Done | 2015-11-03 | 2016-01-05 | 2016-01-11 | 11th Jan | NA | 12th Jan | 19th Jan | 25th May | 2016-06-08 |  | Pending | Pending | Done |  |  | Pending | Pending | [5 empty] | Ashna
France | New 2.6 | Live | NA | MD-1069 | Done | 2016-08-08 | 2016-02-08 | 2016-02-28 | NA | NA | 1st Mar | 8th Mar | 15th May | 2016-06-02 |  | Done | Done | Done | Done | Done | Done | 2.6 Unipro | [5 empty] | Done
Gulf Levant | New 2.6 | Build | NA | MD-753 | MLR | 2015-09-15 | 2016-09-14 | 2016-08-25 | 29th Aug | 12th Sep | 30th Aug | 6th Sep | 1st Sep | 2016-09-21 | Rachit | [12 empty] | NA
Ireland | 2.3 - 2.6 | Soft Launch | 46200 |  | Done | 2016-02-02 | 2016-03-17 | 2016-03-22 | 22nd Mar | NA | 23rd Mar | 29th Mar | 20th June | 2016-07-01 |  | Done | Done | Done | Done | Done | Pending | Done | [5 empty] | Ashna
Italy | New 2.6 | Live |  | MD-877 | Done | 2016-05-23 | NA | NA | NA | NA | NA | NA | NA | 2016-07-21 |  | Done | Done | Done | FFW | Done | Done | Done |  | FFW | Completed | Completed | Completed | Done
Korea | 2.2 - 2.6 | Live | 51378 | MD-1311 | Done | 2016-01-29 | NA | NA | NA | NA | NA | NA | NA | 2016-05-12 |  | Done | Done | Done | Pending | Done | Pending | Pending |  |  | Pending | Done | Done | Pradeep
Malyasia | New 2.6 | Soft Launch | 41678 | MD-919 | Done | 2015-10-06 | 2016-02-04 | 2016-02-08 | NA | NA | NA | NA | NA | 2016-07-29 |  | Done | Done | Done | Done | Done | Pending | Pending |  |  | In Progress |  |  | Ashna
Mexico | 2.3 - 2.6 | MTP | 63730 | MD-1190 | MLR | 2016-01-13 | 2016-07-12 | 2016-07-18 | 19th July | 3rd Aug | 18th July | 26th July | 2016-08-23 | 2016-09-07 | [6 empty] | Pending | Pending | [5 empty] | NA
Netharland | 2.3 - 2.6 | Live |  |  | Done | 2015-10-05 | NA | NA | NA | NA | NA | NA | NA | 2016-04-25 |  | Done | Done | Done | Done | Done | Done | Done |  |  | Pending |  |  | Done
Norway | New 2.6 | Live | 41971 | MD-1147 | Done | 2016-01-04 | NA | NA | NA | NA | NA | NA | NA | 2016-06-27 |  | Done | Done | Done | Done | Done | Done | Pending | [5 empty] | Ashna
Philippines | 2.2 - 2.6 | Live | 53432 | MD-1234 | Done | 2016-01-18 | 2016-05-16 | 2016-05-19 | 3rd June | 17th June | NA | NA | NA | 2016-06-30 |  | Done | Done | Done | Done | Done | Done | Done | Done |  | Pending | Pending | Pending | Done
Romania | 2.3 -2.6 | MTP |  |  | Done | 13th May | 2016-07-21 | 2016-07-27 | 27th July | 10th Aug | 28th July | 3rd Aug | 2016-08-24 | 2016-08-31 | Ghanendra Kumar | [12 empty] | NA
Russia | 2.3 - 2.6 | Live | 41972 | MD-928 | Done | 2015-12-28 | NA | NA | NA | NA | NA | NA | NA | 2016-04-21 |  | Done | Done | Done | Done | Done | Done | Deborah | [5 empty] | Ashna
Saudi Arabia | 2.3 - 2.6 | Env Creation | 68367 | MD-1710 | Done | 2016-06-14 | 2016-08-22 | 2016-08-24 | 2016-08-26 | 12th Sep | 2016-08-29 | 2016-09-02 | 2016-10-01 | 2016-10-19 |  | Pending | Pending | Done | Done | Pending | Pending | Pending | [5 empty] | NA
Spain | New 2.6 | Live | 40806 | MD-1108 | Done | 2015-12-21 | 2016-02-15 | 2016-02-18 | NA | NA | NA | NA | NA | 2016-06-20 |  | Done | Done | Done | Done | Done | Done | 6th June | [5 empty] | Done
Switzerland | New 2.6 | Build |  |  |  | 2016-05-16 | 2016-09-02 | 2016-07-27 | 29th July | 12th Aug | 1st Aug | 5th Aug | 14th Sep | 2016-09-29 | Rachit | [12 empty] | NA
Taiwan | 2.2 - 2.6 | MTP | 67228 | MD-1376 | Done | 2016-06-03 | 2016-08-10 | 2016-08-12 | 16th Aug | 31st Aug | 17th Aug | 23rd Aug | 26th Sep | 2016-10-10 |  | Done | Done | Done | Done | Done | Done | Pending | [5 empty] | Sayed
Turkey | New 2.6 | Soft Launch | 56222 | MD-873 | 2.7 | 2015-10-12 | NA | NA | NA | NA | NA | NA | NA | 2016-06-10 |  | NA | Done | Done | Done | Done | Pending | Pending |  |  | Completed |  |  | Eitisha
UK | New 2.6 | Live |  | MD-873 | FFW | 2015-09-21 | NA | NA | NA | NA | NA | NA | NA | 2016-04-14 |  | Done | No | Done | FFW | Done | Done | Done | Done | FFW | Completed | Completed | Completed | Pradeep
Venezuela | 2.3 - 2.6 | MTP | 62301 | MD-931 | Done | 2016-01-05 | 2016-06-30 | 2016-07-05 | 8th July | 22nd july | 11th July | 19th July | 18th Aug | 2016-08-31 | Rachit Gupta | 7.x-hcp-2.3.3 | 7.x-hcp-2.2.2 | 7.x-hcp-2.3.3 | 7.x-hcp-2.6.8 | 7.x-hcp-2.6.x-dev |  | Done | 7.x-hcp-2.6.10 |  |  |  |  | Sayed
New Zealand | New 2.7 | Build |  |  | Build | 2016-09-05 | 2016-11-08 | 2016-11-10 | 2016-11-14 | 2016-11-29 | 2016-11-14 | 2016-11-21 | 2017-02-10 | 2017-02-27
Czech Rep | New 2.7 | Build |  |  | Build | 2016-09-19 | 2016-11-21 | 2016-11-23 | 2016-11-28 | 2016-12-12 | 2016-11-29 | 2016-12-05 | 2017-01-13 | 2017-02-01
Egypt | 2.3 - 2.6 | Build |  |  | Build | 2016-10-03 | 2016-12-06 | 2016-12-08 | 2016-12-12 | 2016-12-26 | 2016-12-13 | 2016-12-19 | 2017-01-15 | 2017-02-03
Poland | New 2.7 | Build | 67366 | MD-1636 | Done | 2016-06-03 | 2016-08-05 | 2016-08-10 | 2016-08-18 | 2016-09-05 | 16 auh 16 | 2016-08-22 | 2016-09-14 | 2016-09-29
Israil | New 2.7 | Build |  |  | Build | 2016-07-25 | 2016-09-21 | 2016-09-26 | 2016-09-27 | 2016-10-11 | 2016-09-28 | 2016-10-04 | 2016-11-14 | 2016-12-01
Sweden | New 2.7 | Build |  | ` | Done | 2016-07-05 | 2016-08-24 | 2016-08-26 | 2016-09-02 | 2016-09-16 | 2016-08-31 | 2016-09-07 | 2016-10-21 | 2016-11-10
Hungry | New 2.7 | UAT | 71444 | MD-1843 | Done | 2016-07-05 | 2016-09-01 | 2016-09-06 | 2016-09-08 | 2016-09-16 | 2016-09-09 | 2016-09-15 | 2016-11-25 | 2016-12-11
Belgium | New 2.7 | Build |  |  | Build | 2016-07-14 | 2016-09-19 | 2016-09-21 | 2016-09-23 | 2016-10-07 | 2016-09-22 | 2016-09-28 | 2016-11-07 | 2016-11-22
Greece | New 2.7 | Build |  |  |  | 2016-06-14
Germany

## 2.7 Gold Market
Country | Upgrade Version | Status | Zendesk | JIRA Epic | Dev5 Handover | Upgrade Start | Content Remediation 1 | UAT and KT |  | Signoff date | Warrenty Ends | Dev5 to Stage | Go-Live Actiivty Start | Launch | Content remediation II | Dev4 to Dev3 Sync | Other Dev Env Start | Other Dev Env Ends | Dev Envs | [8 empty] | Tested Self Service (Dev -> Dev2) | Tested Self Service (Dev3 -> stage) | Tested Self Service (stage -> Prod | Owner
[7 empty] | Dev3 to Dev5 | Start Date | End Date | [9 empty] | Dev | Dev2 | Dev3 | Dev4 | Dev6 | Dev7 | Dev 8 | Stg | Stg2
[19 empty] | Status | Status | Status | Status | Status | Status | Status | Status | Status
Denmark | 2.6 - 2.7 | Done |  |  | 2016-06-27 | 2016-05-23 | 4 July - 8 July | 2016-06-27 | 2016-07-08 | 2016-07-11 | 2016-07-25 | 2016-07-26 | 2016-07-25 | 2016-08-01 | 25 July - 10 Aug | 2016-08-12
Italy | 2.6 - 2.7 | Build | 68927 |  | 2016-07-04 | 2016-06-06 | 4 July - 8 July | 2016-07-04 | 2016-07-15 | 2016-07-21 | 2016-08-08 | 2016-09-28 | 2016-09-25 | 2016-10-05 | 26 Sep - 4 Oct | 2016-10-06 | 2016-10-07 | 2016-10-12
UK | 2.6 - 2.7 |  |  |  | 2016-08-03 | 2016-05-23 | 27 June - 5 July | 2016-08-05 | 2016-08-09 | 2016-08-09 | 2016-08-24 | 2016-08-10 | 2016-08-01 | 2016-08-11 | 10 Aug - 18 Aug | 2016-08-22 | 2016-08-23 | 2016-08-26
Turkey | 2.6 - 2.7 | Build |  |  | 2016-09-09 | 2016-08-01 | 5 Sep - 16 Sep | 2016-09-12 | 2016-09-16 | 2016-09-19 | 2016-10-04 | 2016-09-28 | 2016-09-25 | 2016-10-04 | 27 Sep - 6 Oct | 2016-10-12 | 2016-10-13 | 2016-10-19
France | 2.6 - 2.7 | UAT | 72117 | PUVTMM-214 | 2016-09-07 | 2016-07-25 | 29 Aug - 9 Sep | 2016-09-07 | 2016-09-13 | 2016-09-14 | 2016-09-29 | 2016-09-29 | 2016-09-20 | 2016-10-03 | 19 Sep - 28 Sep | 2016-10-03 | 2016-10-04 | 2016-10-10
Russia | 2.6 - 2.7 | Build |  |  | 2016-09-19 | 2016-08-15 | 10 Sep - 30 Sep | 2016-09-19 | 2016-09-23 | 2016-09-26 | 2016-10-12 | 2016-10-11 | 2016-10-01 | 2016-10-17 | 10 oct - 19 oct | 2016-10-24 | 2016-10-25 | 2016-11-02
Spain | 2.6 - 2.7 | Build |  |  | 2016-10-17 | 2016-09-19 | 17 Oct - 28 Oct | 2016-10-17 | 2016-10-21 | 2016-10-24 | 2016-11-09 | 2016-11-08 | 2016-11-01 | 2016-11-14 | 7 Nov- 16 Nov | 2016-11-21 | 2016-11-22 | 2016-11-28
Concerns

## 2.7 Silver market
Country | Upgrade Version | Status | Zendesk | JIRA Epic | Dev5 Handover | Upgrade Start | UAT and KT |  | Signoff date | Warrenty Ends | Dev5 to Stage | Go-Live Actiivty Start | Launch | Dev4 to Dev3 Sync | Other Dev Env Start | Other Dev Env Ends | Envs | [8 empty] | Tested Self Service (Dev -> Dev2) | Tested Self Service (Dev3 -> stage) | Tested Self Service (stage -> Prod | Owner
[7 empty] | Start Date | End Date | [8 empty] | Dev | Dev2 | Dev3 | Dev4 | Dev6 | Dev7 | Dev 8 | Stg | Stg2
[17 empty] | Status | Status | Status | Status | Status | Status | Status | Status | Status
Portugal | 2.6 - 2.7 | QA | 71620 | PUVTMM-273 | 2016-09-05 | 2016-08-10 | 2016-09-08 | 2016-09-13 | 2016-09-15 |  | 2016-09-26 | 2016-09-15 | 2016-10-03 | 2016-10-04 | 2016-10-05 | 2016-10-11
Norway | 2.6 - 2.7 | Build |  |  | 2016-09-14 | 2016-08-18 | 2016-09-16 | 2016-09-22 | 2016-09-26 |  | 2016-10-06 | 2016-09-25 | 2016-10-13 | 2016-10-14 | 2016-10-17 | 2016-10-21
Netherlands | 2.6 - 2.7 | Build |  |  | 2016-09-12 | 2016-08-23 | 2016-09-19 | 2016-09-21 | 2016-09-23 |  | 2016-10-03 | 2016-09-15 | 2016-10-10 | 2016-10-07 | 2016-10-11 | 2016-10-14
Finland | 2.6 - 2.7 | Build |  |  | 2016-10-25 | 2016-09-26 | 2016-10-25 | 2016-11-08 | 2016-11-10 |  | 2016-11-22 | 2016-11-05 | 2016-11-30 | 2016-11-30 | 2016-12-01 | 2016-12-07
Ireland | 2.6 - 2.7 | Build |  |  | 2016-10-03 | 2016-09-06 | 2016-10-05 | 2016-10-11 | 2016-10-13 |  | 2016-10-25 | 2016-10-15 | 2016-11-01 | 2016-11-02 | 2016-11-02 | 2016-11-09
Romania | 2.6 - 2.7 | Build |  |  | 2016-11-30 | 2016-11-07 | 2016-12-05 | 2016-12-09 | 2016-12-13 |  | 2017-01-05 | 2016-01-01 | 2017-01-12 | 2017-01-02 | 2017-01-20 | 2017-01-25
Austria | 2.6 - 2.7 | Build |  |  | 2016-11-21 | 2016-10-24 | 2016-11-21 | 2016-11-30 | 2016-12-02 |  | 2016-12-14 | 2016-12-01 | 2016-12-21 | 2016-12-22 | 2016-12-22 | 2016-12-26
Switzerland | 2.6 - 2.7 | Build |  |  | 2016-12-07 | 2016-11-14 | 2016-12-12 | 2016-12-16 | 2016-12-20 |  | 2017-01-13 | 2017-01-01 | 2017-01-20 | 2017-12-21 | 2017-12-21 | 2017-12-27

## freeze Periods
Market |  | Code Freeze |  | Content Freeze
Category | Country | Code freez start | Code Freeze End | Content freeze start | Content freeeze End
SILVER | Portugal | 2016-08-10 | 2016-10-03 | 2016-09-16 | 2016-03-10
| Norway | 2016-08-18 | 2016-10-12 | 2016-09-27 | 2016-12-10
| Netherlands | 2016-08-23 | 2016-10-10 | 2016-09-23 | 2016-10-10
| Finland | 2016-09-05 | 2016-10-31 | 2016-10-14 | 42674
| Ireland | 2016-09-26 | 2016-11-25 | 2016-09-11 | 42699
| Romania | 2016-11-07 | 2017-01-18 | 2016-12-21 | 42753
| Ausrtia | 2016-10-24 | 2016-12-27 | NA | NA
| Switzerland | 2016-11-14 | 2017-01-23 | NA | NA
GOLD | Denmark | 2016-05-23 | 2016-08-12 | 2016-07-04 | 2016-08-01
| Italy | 2016-05-23 | 2016-09-21 | 2016-09-26 | 2016-10-06
| UK | 2016-05-23 | 2016-08-26 | 2016-08-02 | 2016-08-12
| Turkey | 2016-08-01 | 2016-10-11 | 2016-09-19 | 2016-10-03
| France | 2016-07-25 | 2016-10-03 | 2016-09-12 | 2016-09-26
| Russia | 2016-08-15 | 2016-10-24 | 2016-10-03 | 2016-10-17
| Spain | 2016-09-12 | 2016-11-21 | 2016-10-31 | 2016-11-14