## Checklist
Deployment Checklist for: Netherlands |  |  |  | Platform | 7.x-hcp-2.7.7 | Updated: | 2016-09-13 | Martin Malovanets | Target MTP date:
| HCP 2.7 |  |  |  |  | Production: | URL | www.pfizerpro.nl | Stage: | pfpfpronlstg.prod.acquia-sites.com (2.6.9)
[7 empty] | Project Team POC | Project Team | Dev3 | pfpfpronldev3.prod.acquia-sites.com (2.6.9)
[7 empty] | L3 Team POC | L3 Team | Dev5 | pfpfpronldev5.prod.acquia-sites.com (2.7.7)
[7 empty] | Content Team POC | Content Team | Latest Code | dev5
[7 empty] | Pfizer BT POC | BT | Latest Content
[7 empty] | Support POC | HCP Support
# | Group | Item | Category | Timeframe Prior to MTP (days)? |  | Done? | Owner | Date Complete | Confirmed By | Notes
1 | General | If site is Soft Launced? |  |  |  |  | HCP Support
2 | General | If market solft launced, Has MTP package received from Project team? |  |  |  |  | HCP Support
3 | General | On which enviroemnt is the latest code residing |  |  |  |  | L3 Team
4 | General | On which environment is the latest content residing |  |  |  |  | Content Team
5 | General | Are CPE/STG/PROD having same platform and HCP subplatform? |  |  |  | No | HCP Support | 2016-09-13 | Martin Malovanets
6 | General | Are there any open Zendesk tickets for this portal? |  |  |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets | No zendesk tickets related to this upgrade that our team is aware of
7 | SDLC | Has a Compliance Risk Profile (CRP) & a CMDB record been generated? https://docs.digitalpfizer.com/sdlc-documentation/cmdb-iprm | Security | 30 |  |  | Project Team
8 | SDLC | Has the translation template been completed by the market? |  | Prior to MTP |  | N/A | HCP Support | 2016-09-13 | Martin Malovanets
9 | DNS | Verify the domain name is secured and using a standard Pfizer name server. http://www.whois.com or other in-market service | DNS | ASAP |  |  | BT
10 | Security | Is SSL certificate configured for primary domain. (Any page that captures user information needs to be on SSL) | SSL | 15 |  | N/A | HCP Support | 2016-09-13 | Martin Malovanets | Site is live
11 | Metrics | Is Omniture Report suite configured? |  | 15 |  | Yes | HCP Support |  |  | Test cases and report provided - Page and Features
12 | Acquia | Check that the production environment has 160MB of APC memory set https://www.pfpfproXX.prod.acquia-sites.com/ACQUIA_MONITOR Raise a support ticket if not to get this fixed. |  | 15 |  | N/A | HCP Support | 2016-09-13 | Martin Malovanets | We don’t have access to this anymore -
13 | Acquia | Confirm with BT Support that system CRON is enabled on production to run every 15 minutes (4 times an hour) |  | 7 |  | N/A | HCP Support | 2016-09-13 |  | Site is live
14 | Custom | Have any custom code been written by Project Team? Is code reviewed? | - | 7 |  | Yes | HCP Support | 2016-09-13 |  | Coder report provided
15 | Custom | Have any custom code been written by L3 support team? Is code reviewed? | - | 7 |  |  | L3 Team
16 | SDLC | Have you reviewed JIRA for open tickets? https://smscvt.atlassian.net/ |  | 7 |  | Yes | HCP Support | 2016-09-13 |  | https://digitalpfizer.atlassian.net/browse/PUVTMM-276
17 | Custom | Has Project Team run the Coder Report on custom modules/code and upload these reports to the deployment documents folder? | Deploy | 5 |  | Yes | HCP Support | 2016-09-13 |  | Attached
18 | Custom | Has L3 Team run the Coder Report on custom modules/code and upload these reports to the deployment documents folder? | Deploy | 5 |  |  | L3 Team
19 | Janrain | Have you notified the Janrain team of Production deployment schedule (email at least one week in advance)? | GRV | 7 |  | N/A | HCP Support |  |  | Site is live
20 | Janrain | Have you confirmed that final, approved GRV screens have been deployed to GRV Production (Amazon)? https://github.com/pfizer/janrain_capture_screens | GRV | 5 |  | N/A | HCP Support | 2016-09-13 | Martin Malovanets | Site is live
21 | Kuluvalley | Is pfizer_kuluvalley enabled? Has the Kulu Valley player configurations for DEV been confirmed and added to local.settings.php? | Kulu Valley | 5 |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets
22 | Kuluvalley | Has the Kulu Valley player configurations for Stage and Production been confirmed and added to local.settings.php? | Kulu Valley | 5 |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets
23 | Janrain | Is pfizer_grv enabled? |  | 5 |  | Yes | HCP Support
24 | Janrain | Have you requested the Production GRV configuration information and verified the correct settings in the local.settings.php file? |  | 5 |  | Yes | HCP Support |  | Martin Malovanets | Site is live. GRV functionality not affected
25 | Pitcher | (2.3) Has Pitcher Client creation been requested from BT-SUPPORT? Has Pitcher been enabled ( pfizer_pitcher ) and configured for site? |  | 5 |  | N/A | HCP Support | 2016-09-13 | Martin Malovanets
26 | Pitcher | (2.3) If eDetails is enabled (pfizer_hcp2_edetail pfizer_hcp2_edetail_pitcher pfizer_hcp2_edetail_perms) verify that platform is 2.3.3 or greater |  | 5 |  | N/A | HCP Support | 2016-09-13 | Martin Malovanets
27 | Branding | (2.3.3) Remove pfizer_pro_product_branding module if it exists ( this feature now incorporated into 2.3.3) |  | 5 |  | N/A | HCP Support | 2016-09-13 | Martin Malovanets | Not present
28 | Branding | Has custom branding S3 host been configured for each of the environments(Dev/Stg/Prod) in Local.settings.php $conf[pfizer_pro_s3_bucket]? |  | 5 |  |  | L3 Team
29 | Content | Verify "Full HTML with Scripts" Text Format for Brightcove. /admin/config/content/formats |  | 5 |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets
30 | Performance | Confirm with BT Support that Acquia has enabled "Varnish through SSL" option. |  | 5 |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets | Currently enabled in Prod
31 | Janrain | If integrating with 3rd party validation, insure production domain name has been whitelisted with Janrain prior to launch, Email (DL-BT-DIGITALMARKETING@pfizer.com) to confirm. | GRV | 5 |  | N/A | HCP Support
32 | Content | Has the portal "demo" content been removed and un-published from the site and Brands feed? |  | 5 |  |  | Content Team
33 | Migration | Do we have PMI (PfizerMedInfo) built for the market in question? And if so, is there interconnectivity of the authentication solution in place? | - | 5 |  |  | BT
34 | Migration | If preexisting site, has Pfizer Connect user data migration been completed for this market to the new GRV solution? | GRV | 5 |  |  | BT
35 | SDLC | Has the SDLC Deployment Document been completed for Code Changes (must be sent with MTP documentation prior to the deployment)? | MTP | Min. 3 days prior to MTP |  |  | L3 Team
36 | SDLC | Has the SDLC Deployment Document been completed for Content Changes (must be sent with MTP documentation prior to the deployment)? | MTP | Min. 3 days prior to MTP |  |  | Content Team
37 | SDLC | Has the business unit sent approval email? Include approval email in Deployment Plan documentation. | MTP | Min. 3 days prior to MTP |  |  | BT
38 | SDLC | Have you scheduled the MTP with the Support Team (email to DL-BT at least 3 days in advance of deployment date)? | MTP | Min. 3 days prior to MTP |  | N/A | HCP Support
39 | SDLC | Has the BT Solutions Center sent approval email? Include approval email in Deployment Plan documentation. | MTP | Min. 3 days prior to MTP |  |  | BT
40 | Janrain | Confirm GRV configuration information for Production is included in the Deployment Plan. | GRV | Min. 3 days prior to MTP |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets
41 | Custom | Create changelog.txt in the GitHub directory and fill in details of what has been customised whilst deploying this Portal. |  | Prior to MTP |  |  | L3 Team
42 | Janrain | Delete all GRV test accounts, disable all non-essential Drupal accounts |  | Prior to MTP |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets | user table will be skipped during MTP
43 | Custom | pfizer_pro_product_branding - If used verify that Brands.css and Brands.js files are moved into production S3 bucket - https://github.com/pfizer/pfizerpro-global-s3 |  | Prior to MTP |  | N/A | HCP Support | 2016-09-13 | Martin Malovanets
44 | Kuluvalley | If KuluValley is enabled have the Webinar email settings been configured? /admin/config/system/pfizer_hcp/webinar |  | Prior to MTP |  | Yes | HCP Support
45 | Brightcove | Has the BrightCove configuration for Production been confirmed and added to local.settings.php? | BrightCove | Prior to MTP |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets
46 | Language | Has the site been translated into market's language(s). Are Language settings correctly set to support single or multiple languages. | Deploy | Prior to MTP |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets
47 | SDLC | Have you read & followed the Pfizer technical standard guides: Drupal Custom | Deploy | Prior to MTP |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets
48 | SDLC | Have you read & followed the Pfizer technical standard guides: Drupal Custom | Deploy | Prior to MTP |  |  | L3 Team
49 | Security | Has the security test been completed and approved? Include approval email in Deployment Plan documentation. | Security | Prior to MTP |  |  | L3 Team
50 | Security | Has the security test been completed and approved? Include approval email in Deployment Plan documentation. | Security | Prior to MTP |  |  | L3 Team
51 | Security | Have you completed the securepages configuration? Have you confirme that /user and /admin pages are using SSL. | Deploy | Prior to MTP |  | N/A | HCP Support | 2016-09-13 | Martin Malovanets | We didn’t configure any since market is live
52 | Security | secure cookies have been enabled? $conf['https'] = FALSE; | Deploy | Prior to MTP |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets
53 | Content | Have you removed and/or updated the favicon.ico | Omniture / IM | Prior to MTP |  |  | Content Team
54 | Security | Ensure that anonymous users do not have elevated permissions. Make sure anonymous user does not have permission to create account on sites (unless its business requirement). admin/config/people/accounts | Deploy | Prior to MTP |  |  | L3 Team
55 | Security | Have you verified configuration for new Drupal pages. Make sure anonymous users DO NOT have admin rights to view unpublished, create, or update nodes/pages. /admin/people/permissions | Deploy | Prior to MTP |  |  | L3 Team
56 | Performance | Has Drupal and Varnish cache been enable on site? Please refer to Improving website performance: https://docs.digitalpfizer.com/drupal-custom-development/improving-website-performance | Deploy | Prior to MTP |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets
57 | Metrics | Confirm Omniture / Web Standards module is enabled (pfizer_webstandards_hcp2) and configurations are in local.settings.php. Review the actual suite in SiteCatalyst to see if the events are indeed firing correctly and the correct suite name is being used on dev and prod. Ensure any dev settings have been removed or deprecated so they do not impact production. Check ALL specific events, e.g. registration, event registration etc. | Omniture / IM | Prior to MTP AND Day of MTP |  |  | L3 Team
58 | Performance | Have routes for vanity urls been created, including non-www url to the primary domain? (Platform team will procure SSL for only for primary domain.) Redirect for both http and https. apache_custom.conf | DNS | Prior to MTP |  | Yes | L3 Team
59 | Security | Have reoutes been created to route user/login, user/password, and user/register to /login? |  | Prior to MTP |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets | We didn’t configure any since market is live
60 | Content | Is the Web service connectivity (ie: Brands feed) configured as per the required environments in Local.settings.php (stage/production) ? | - | Prior to MTP |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets
61 | Security | Verify that Devel and Backup & Migrate have been disabled on production |  | Prior to MTP |  | Yes | HCP Support
62 | Content | Verify that Deploy is enabled/disabled per market requirements. | DNS | Prior to MTP |  | Yes | HCP Support |  |  | Deploy module enabled
63 | Metrics | Do you need a specific page (other than the home page) to be added to the support monitoring solution? | Support | Min. 3 days prior to MTP |  |  | BT
64 | Custom | Confirm Behat tests completed and passed. | - | N/A |  |  | L3 Team
65 | SDLC | Confirm production deployment Git tag. | Deploy | Day of MTP |  |  | HCP Support
66 | SDLC | Has the approved site been pushed to stg for MTP? |  | Min. 3 days prior to MTP |  |  | HCP Support
67 | General | Are amazon S3 files(CSS/JS/Assets) moved from Dev to Stg bucket? |  |  |  | N/A | HCP Support | 2016-09-13 | Martin Malovanets
68 | SDLC | Have you completed the KT Checklist and documentation? |  | N/A |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets
69 | SDLC | Have you scheduled the KT Meeting? |  | N/A |  |  | HCP Support
70 | Janrain | IF moving GRV into production for the first time, advise Chris L so that he can enable production GRV Admin Tool. | SSL | Day of MTP |  | N/A | HCP Support
71 | Content | Prior prod launch check with Oleg to ask if the prod domains were whitelisted for fontdeck.com |  | Prior to MTP |  | N/A | HCP Support | 2016-09-13 | Martin Malovanets | Site is live n/a
72 | Acquia | Make sure $_ENV is used instead of $_SERVER in local.settings.php |  | Prior to MTP |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets
73 | Security | Make sure your deployment instruction have "Allow login" set to "YES" since this is a requirement for GRV |  | Day of MTP |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets
74 | Performance | Is Memcache configured correctly within local.settings.php? |  | Prior to MTP |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets
75 | Performance | Is the memory_limit set to at least 512 in local.setting.php for all environments |  | Prior to MTP |  | Yes | HCP Support | 2016-09-13 | Martin Malovanets
76 | GRV | GRV Admin Tool Onboarding for a country business person, who will be managing GRV users for the country |  | Prior to MTP |  |  | BT
77 | General | Anonymous user shouldn’t see the home and product pages |  |  |  |  | L3 Team

## BT Questions
BT need to respond to below queries before Go Live
Verify the domain name is secured and using a standard Pfizer name server. http://www.whois.com or other in-market service
Do we have PMI (PfizerMedInfo) built for the market in question? And if so, is there interconnectivity of the authentication solution in place?
If preexisting site, has Pfizer Connect user data migration been completed for this market to the new GRV solution?
Has the business unit sent approval email? Include approval email in Deployment Plan documentation.
Has the BT Solutions Center sent approval email? Include approval email in Deployment Plan documentation.
Do you need a specific page (other than the home page) to be added to the support monitoring solution?
GRV Admin Tool Onboarding for a country business person, who will be managing GRV users for the country

## L3 Team Questions
L3 need to respond to below queries before MTP
On which enviroemnt is the latest code residing
Have any custom code been written by L3 support team? Is code reviewed?
Has L3 Team run the Coder Report on custom modules/code and upload these reports to the deployment documents folder?
Has custom branding S3 host been configured for each of the environments(Dev/Stg/Prod) in Local.settings.php $conf[pfizer_pro_s3_bucket]?
Has the SDLC Deployment Document been completed for Code Changes (must be sent with MTP documentation prior to the deployment)?
Create changelog.txt in the GitHub directory and fill in details of what has been customised whilst deploying this Portal.
Have you read & followed the Pfizer technical standard guides: Drupal Custom
Has the security test been completed and approved? Include approval email in Deployment Plan documentation.
Ensure that anonymous users do not have elevated permissions. Make sure anonymous user does not have permission to create account on sites (unless its business requirement). admin/config/people/accounts
Have you verified configuration for new Drupal pages. Make sure anonymous users DO NOT have admin rights to view unpublished, create, or update nodes/pages. /admin/people/permissions
Confirm Omniture / Web Standards module is enabled (pfizer_webstandards_hcp2) and configurations are in local.settings.php. Review the actual suite in SiteCatalyst to see if the events are indeed firing correctly and the correct suite name is being used on dev and prod. Ensure any dev settings have been removed or deprecated so they do not impact production. Check ALL specific events, e.g. registration, event registration etc.
Have routes for vanity urls been created, including non-www url to the primary domain? (Platform team will procure SSL for only for primary domain.) Redirect for both http and https. apache_custom.conf
Confirm Behat tests completed and passed.
Anonymous user shouldn’t see the home and product pages