## Smoke test check-list
BT Digital CoE Minimal Risk Requirements & Verification
# | Requirement or User Story Description | Tester Name | Date Executed | Behat Test Available (Yes or No) | Criticality/ Severity (H, M, L) | Rigor of Verification (I, S, M) | Test Case Description | Expected result | Actual Result: Pass Fail N/A Skipping | Issue description/screenshots | Jira Ticket URL | Evidence Included for Intensive or Standard test cases? (Yes or No)
1 | Configuration check |  |  | No | H | S
|  | Arthur | 2016-07-09 | No | H | S | Platform version check: Proceed to the site and click f12 and serch for the "hcp-version" | Platform version should be 7.x-2.7.7 | Pass |  |  | No
| New: MHPE-740 PFHCPXMB-8 Add support for XREF Multiple Brand URLs To add this functionality, you need to enable the new module 'pfizer_hcp2_brand_urls'. | Arthur | 2016-07-09 | No | H | S | Features (admin/structure/features) | Portal-specific features that should be enabled: In HCP Portal Advanced - all should be enabled except - Pfizer HCP2 Example Content, Pfizer HCP2 Example Config, pfizer_hcp2_web_standards, Pfizer HCP2: Velaro Chat , (pfizer_webstandards_hcp2 should be enabled); In Pfizer - Pfizer Mailgun - should be enabled In Pfizer Base Features - all should be enabled In Pfizer Web Standards - Pfizer Web Standards should be enabled (but that might varry based on the features they opt in. Ie if they dont want webinars it is ok not to have that feature enabled , if they dont want contact widget it is ok not to have that enabled etc) | Pass |  |  | No
|  | Arthur | 2016-07-09 |  |  |  | Modules which should be installed and enabled | This is a list of MANDATORY modules, that have to be present and enabled on all projects: "Acquia Connector" section consists of three modules, all of which should be enabled pfizer_administration pfizer_deploy pfizer_performance pfizer_security pfizer_xmlsitemap pfizer_profile - You can check the status report for Pfizer (Acquia) Profile at: /admin/reports/status pfizer_kuluvalley, pfizer_pitcher - should be enabled pfizer_hcp2_brand_urls - should be enabled Custom modules for Netherlands: hcp_overrides - should be enabled pfizer_grv_webhooks pfizer_hcp_erf pfizer_hcp2_conditions pfizer_hcp2_products | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Webinars - Kulu Valley player configuration /admin/config/media/kuluvalley | KuluValley settings should be correctly entered. Please see the document, refer to "KV config" tab here https://docs.google.com/spreadsheets/d/1Ztl8UuGzhqxHAW94ZeZZmo-BUnP_f9WSdquin2C5Fw0/edit?pli=1#gid=1459186980 First red line it is default setting for all dev and stage environments. But because of issue on KV uat environment, currently we should use settings for production. http://prntscr.com/cfzlwt | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Omniture settings - SiteCatalist settings /admin/config/system/sitecatalyst | SiteCatalist settings should be filled properly. https://s3.amazonaws.com/pfe_im/js/dev/s_code.js https://pfizer.112.2o7.net/b/ss/pfizerglobalimdevelopment/1/JS-1.2.2--NS/0 JS-1.2.2 User roles tracking: admin, anonymous, authenticated user, Content Diff `User role tracking` should be set to `Add to the selected roles only` -> http://screencast.com/t/CbIxhK7ueFU | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Omniture settings - WebStandart settings /admin/config/system/webstandards | WebStandard settings should be filled properly For dev and stage sites should be set up correct market specific and global suites id For production suites should be different and properly set up: market specific+global See the details for each market here https://blinkreaction.atlassian.net/wiki/display/PMCG14/HCP+Omniture+Integration | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Mail server check - Email /admin/config/system/smtp | Mail settings should be filled properly. | Pass |  |  | No
[7 empty] | SMTP Hostname | smtp.mailgun.org |  |  |  | No
[7 empty] | Login | postmaster@pfizerpro.mailgun.org |  |  |  | No
[7 empty] | Pass | 1zznevbtv1n4 |  |  |  | No
[7 empty] | SMTP Port | 587 |  |  |  | No
[7 empty] | Use encrypted protocol | Use TLS |  |  |  | No
[7 empty] | Email from | admin@example.com |  |  |  | No
[7 empty] | Email from name | Pfizer HCP |  |  |  | No
[7 empty] | Send test email and check if it received | Email should be received, no need to run cron |  |  |  | No
2 | Site overview
|  | Arthur | 2016-07-09 |  |  |  | Open dev5 and stg2 and production www.pfizerpro.nl |  |  |  |  | No
|  | Arthur | 2016-07-09 |  |  |  | Compare header and footer | Header and footer should include itself the same text and links, and all should be aligned properly | Pass |  |  | No
|  | Arthur | 2016-07-09 |  |  |  | Check Page Title, Logo, Main Menu, Sign in/Register link names | All should match | Pass |  |  | No
|  | Arthur | 2016-07-09 |  |  |  | Cookie popup | Cookie popup shouid be visible and work properly, text and link inside should match | Skipped | https://digitalpfizer.atlassian.net/browse/PUVTMM-359 |  | No
|  | Arthur | 2016-07-09 |  |  |  | Create Webinar - Live Streamed Events | Check if borders are not displayed on live webinar, when user registered to the webinar, and check popups also. | Pass |  |  | No
|  | Arthur | 2016-07-09 |  |  |  | Check 404 Page /404 Page not found /notexistedpage | Should work the same as on stg2 and production | Pass |  |  | No
3 | GRV
|  | Arthur | 2016-07-09 | No | H | S | Check top right Login/Register links | When the user clicks on Register or Login links in the header, they will be redirected to /login page rather than seeing the Register or Login pop up windows opening | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | GRV Login screen, Page after Login | Login should work correctly | Resolved | https://digitalpfizer.atlassian.net/browse/PUVTMM-361 |  | No
|  | Arthur | 2016-07-09 | No | H | S | GRV Register screen, Page after registration | Registration should work correctly. Your account statuse should be "Pending validation". You can should be not able to log in till your account will be validated. Registration email should be received. | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Check Forgot your password GRV screen | Should work as expected, you should able to change your password | N/A |  |  | No
4 | Dual language functionality check - NOT APPLICABLE
|  |  |  | No | H | S | Open content creation page for any type of content and theck language drop-down; Check also on widgets (from Customize this page menu) | It is not Dual language site and there should not be 2 language options, English language should be turned off http://prntscr.com/c6smdw |  |  |  | No
|  |  |  | No | H | S | Search for dual language site | Search should return content only on the selected language |  |  |  | No
|  |  |  | No | H | S | Register, Reminder, Ask questions emails for the webinars | Emails should be on the same language as webinars |  |  |  | No
|  |  |  | No | H | S | Language selector | Content types should have drop down with language selector - English CA and French CA (no only for HCP Pre-event Survey) |  |  |  | No
|  |  |  | No | H | S | Webinar Branding | Only brand with the same language as webinar has should be selectable |  |  |  | No
5 | Search field functionality
| Information: MHPE-660 / MD-940 Seachcontent setting in YAML for anonymous and authenticated users | Arthur | 2016-07-09 | No | H | S | User access for search field | Unavailable to AuthN users | Fixed | https://digitalpfizer.atlassian.net/browse/PUVTMM-360 |  | No
| Note: if search is not working - it can be still global platform issue, create a ticket and ask developers to fix, they can make it working temporary. This way QA will be able to test. | Arthur | 2016-07-09 | No | H | S | Perform search using search field near the main menu, try empty key word, one word, key words that have two words, words that have special symbols | Confirm that: 1. Search should work with empty key word. 2. Search should work with one word 3. Search should work with key words that have two words. 4. Search should work with key words that have special symbols. | Fixed | https://digitalpfizer.atlassian.net/browse/PUVTMM-362 |  | No
| Information: Issue MHPE-657 / MD-913 - Incorrect title on search page. | Arthur | 2016-07-09 | No | H | S | Search something and observe title on search results page | Title should not contain any incorrect symbols. Title should display "Search" | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Observe search results page using URL /search/site, check translation | Search page should provide correct serch results and displayed properly. Should have "Search" header on the banner. Should be translated properly | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Perform search using search field on search results page | Search field on search page should work the same way as search field on the header | Pass |  |  | No
| Hotfix: MHPE-725 High Urgency : Pre-production content appearing in prod search indexes. Critical SOLR issue identified and rectified - requirement added for acquia_search_multi_subs. Also released as part of 7.x-2.5.5 [Should be tested on production only] |  |  | No | H | S | Perform search by the test content only [Should be tested on production only] | Only approved content should appear in search results. Not approved(test) content should not appear in results and should not be indexed. [Should be tested on production only] |  |  |  | No
6 | Product page
|  | Arthur | 2016-07-09 | No | H | S | Jump to for Products on a Product page | You should be able to jump to the correct block of the products by clicking a letter of the alphabet | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Verify popup for external links | If link leades to the different domain so you should be able to see popup and after link should be opened in new tab. | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Check the product links | All links should have correct page opened. All internal links should lead to the same test/stage domain (dev5 should not point to dev3 for example) Each micro-site link should lead to the same page from the quick access block and from the general list - http://prntscr.com/bmo353 http://prntscr.com/bmo3ag | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Check microsites, check translation on microsites | All links should have correct page opened. Pages should opened without issues. Microsites should be translated. | Pass |  |  | No
| Hotfix: PFHCP-949 / MHPE-709 / CN#36898 Issue with product microsite rendering field orders in lists. Critical fix required to address the rendering order of fields in support lists. | Arthur | 2016-07-09 | No | H | S | Proceed to any microsite, click on 'How to Use' link and check that list of links is properly displayed | All links should be properly placed and redirecto appropriate page. Example - https://pfproaustriadev5.prod.acquia-sites.com//support/fuer-ihre-patienten/list | Pass |  |  | No
| Hotfix: MHPE-675 / PFHCP-923 - Styling issue on quick link blocks | Arthur | 2016-07-09 | No | H | S | Open any product and check the text position near the arrow in quicklinks/callouts | The text on mobile should be aligned by the left side and on desktop on the right side. Desktop - http://prnt.sc/9i3sks, mobile/tablet - http://prntscr.com/9i3roq | Pass |  |  | No
| Hotfix: MHPE-663 / MD-987: Incorrect/Missing Context for Selecting Amazon Buckets Blocking Content Teams | Arthur | 2016-07-09 | No | H | S | For any product check that the checkboxes for including CSS and JS from AMAZON S3 bucket are enabled | CSS and JS from AMAZON S3 bucket options should be enabled. Note - Possibly they could be disabled if we have no uploaded file in relevant folder in S3 bucket | Pass |  |  | No
| Hotfix: MHPE-664 / Indication pages : Indication select showing blanks & indications for all brands Hotfix: MHPE-721 / PSHCP-878: added check to ensure that will not added empty row | Arthur | 2016-07-09 | No | H | S | Check that Brand and Indication fields not empty | check that Brand and Indication fields not empty | Pass |  |  | No
| Bugfix: MHPE-718 PFHCP-940 CN#36562 High HCP Premium Netherlands ¦ HCP Netherlands 2.6 title shows at two places | Arthur | 2016-07-09 | No | H | S | 1. Add `hcp_indication` and `hcp_article` nodes 2. Check if welcome text isn't displayed | Welcome text should not be displayed Title should not be shown in 2 places http://prntscr.com/bpgzcu http://prntscr.com/bpgzgi | Pass |  |  | No
| Bugfix: MHPE-731 PFHCP-961 CN#37477 Medium HCP Portal Global ¦ Primary message field validation error in Portal | Arthur | 2016-07-09 | No | H | S | Login as admin 1. Open page for creation new hcp-product /node/add/hcp-products 1. Click save with empty fields - Title, Primary Message, Primary Message Category and Web Asset Type should be highlighted http://prntscr.com/9vva09 3. Fill Başlık, Primary Message Category and Web Asset Type and click save - Primary Message field should be highlighted http://prntscr.com/9vvco5 4. Fill Primary Message field and click save - HCP Product should be added http://prntscr.com/9vvfhh | No errors should appear | Pass |  |  | No
| Bugfix: MHPE-734 ZEND45041 High priority issue for HCP Portal - Support and Services menus are appearing on pages with multiple indications erroneously | Arthur | 2016-07-09 | No | H | S | The issue is that, when viewing a product page which has multiple indications the site should not include any Support and Services links in the mobile menu, however it is. |  | Pass |  |  | No
| Bugfix: MHPE-735 ZEND43254 Problem with displaying private products on the A-Z jump list on the HCP Portal Product Page | Arthur | 2016-07-09 | No | H | S | The problem is this: If you have only got one product with an initial letter, and that product's page is marked as Private then the product appears in the list, but the initial letter does not highlight to allow you to jump to it. http://prntscr.com/bg76fd If you look at the image there is a product, Eliquis - but the letter 'E' is disabled in the jump list. This is because the product is set to 'Private' and the function that builds the list of products displays private products, whilst the function that builds the A-Z list excludes them. | In order to reproduce the issue you need a few things 1) the user MUST be logged out. 2) the variable "pfizer_hcp_private_filtering" must be set to true (e.g. add `$conf'pfizer_hcp_private_filtering' = TRUE;` to local settings' 3) there must be articles for the product 4) all articles for the product must be marked as 'private' (not public or paywall). | Pass |  |  | No
| Hotfix: PFHCP-914 Add check if in panel `title_type` set to `Manually set` | Arthur | 2016-07-09 | No | H | S | Navigate to `admin/config/content/panelizer` -> find the `HCP Article` page -> click `content` button -> http://screencast.com/t/1i6CqiP1ZP |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Set Title type to Manually set, enter some value to below field (e.g %node:title) and hit Save -> http://screencast.com/t/jLgUtoJyVXK |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Navigate to any sub-page for products and there should not be a two titles like here -> http://screencast.com/t/XIoOfdA3Cr | One title should appeare | Pass |  |  | No
| Hotfix: PFHCP-909 Brand CSS files not being renewed post XREF changes | Arthur | 2016-07-09 | No | H | S | Go to any product page or product microsite on the portal under admin and click "Customize this page" and add any block to page | You should be able to customize this page The color of newly created block correspond to the color of the blocks for this product | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Run cron at /admin/config/system/cron and then check that the block on page | The color of newly created block correspond to the color of the blocks for this product and should not be changed after cron run | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Clear all caches at /admin/config/development/performance and then check that the block on page | The color of newly created block correspond to the color of the blocks for this productand should not be changed after clearing the caches | Pass |  |  | No
| Bugfix: MHPE-736 L3 - ZEND42786 Issue with HCP Indication detection | Arthur | 2016-07-09 | No | H | S | Create a HCP Article and brand it as: • Portal content type: Product. • Brand: A brand that has an HCP Brand node created for it. • Indication: A n indication that DOES NOT have a HCP Indication node created for it, or the indication is not published. In these situations, when viewing the article HCP will not be able to correctly identify the indication. | If indication for some brand is not uploaded, check if there is some indication for this brand in json file. To get this json file you should go to /admin/config/hcp/xref open "Inbound Feed Service " section and add to the Service URL the extention Brand Service endpoint (Path) field this way - http://prntscr.com/caoq0u Expected result: If there are no indications as node published and there are no indications in json file and indication is not uploaded for the brand during the Article creation - that is correct behaviour. But if indication exist in json file and was not uploaded on article edit page - this we can report as a bug. | Pass |  |  | No
| Bugfix: MHPE-781 L3 - ZEND66047 - HCP portal break-fix request: exit popup not translating. | Arthur | 2016-07-09 | No | H | S | Click on any links which leads to external link and check if popup for external links appears and translated properly. | Popup for external links should appear and it should be properly translated | Fixed | https://digitalpfizer.atlassian.net/browse/PUVTMM-367
7 | Medical Conditions
|  | Arthur | 2016-07-09 | No | H | S | Go to – medical condition landing page, check translation. Proceed to each sub-page and check if main banner is displayed. | Page should be properly translated. Main banner should be displayed on all sub-pages. | Pass |  |  | No
| Hotfix: PFHCP-925 S&S Navigation reads "support" rather than "condition" for Medical condition microsites | Arthur | 2016-07-09 | No | H | S | Proceed to any sub-page and check right side navigation, check main menu, URL | Right side-bar navigation should work correctly, correct main menu item should be hihlighted. URL should be /medical-conditions | Pass |  |  | No
8 | Material Ordering
|  | Arthur | 2016-07-09 | No | H | S | Open the site as anon user and observe the top main menu and footer | Material ordering section for anon user should not be available in the main menu and via URL also http://prntscr.com/bn14eq | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Try to proceed as anon user using URLs /material-ordering /support/material-ordering |  | Pass |  |  | No
| Hotfix: MD-000 Multilingual variables for Material Ordering 2.6 | Arthur | 2016-07-09 | No | H | S | Go to "Material Ordering" page as authorized user and observe the page | Should be visible for authorized user | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Try to add some items to the basket, check translation in the basket | Should be able to add to the basket and see that backet pop up is shown with changed state and all time is above the rest of the page when page scrolls down. Basket with items is shown in right hand of page prior to completing order. | Pass |  |  | No
| Hotfix: MD-914 Authenticated DRUPAL user cannot remove items from his basket | Arthur | 2016-07-09 | No | H | S | Try to remove items from the basket | Should be able to remove items from basket | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Remove all items from the basket on page with ordering form | You should be redirected to initial material ordering form, basket should be empty and message should appear "Your shopping basket is empty". This message should be properly translated. | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Proceed to the order form page and check fields validation and error messages (translation) | All fields should work properly and error messages should be translated. | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Try to order some items: proceed to the order form, fill all fields with correct data (use real test email) and submit the form. Check translation on the order form page. | Should be able to complete order and confirm can enter information into correct fields. Should be translated properly | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Observe the page after submittiong, check translaion on thank you page | Shoud be able to see order confirmation message after completing order. Translation should be correct. | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Check confirmation email received to the test email. Check translation in this email. | User should receive an email after submitting their order. Email should be translated properly | Pass |  |  | No
9 | User roles/permissions
| Hotfix: MHPE-672 / Permission tweak: allow content editor and content admin to "Create Ad Hoc Deployment Plans" | Arthur | 2016-07-09 | No | H | S | Check that content editor and content admin have "Create Ad Hoc Deployment Plans" permission | "Create Ad Hoc Deployment Plans" permission should be enabled for content editor and content admin. You can find it on user profile page - "Ad Hoc Deployment Plan" tab | Pass |  |  | No
10 | On-demand Event
| oMZVPsEH9YB - Kulu ID | Arthur | 2016-07-09 | No | H | S | Review existing - On-demand Event Videos Note: Use long titles and subtitles etcetera |  | Pass |  |  | No
| Bugfix: MHPE-659 BUG MD-915 KuluValley module not creating thumbnail directory | Arthur | 2016-07-09 | No | H | S | Create new one http://prntscr.com/8sya9d When you add a webinar, the module tries to save a thumbnail to the drupal files directory, but the folder it wants to save to is never created under normal circumstances. Therefore, the thumbail is not saved. In the KV module, there is a reference to $storage_path that is an un-initialized variable, so it's null at that point. The directory never gets created. | This error type should not be shown after webinar creation - http://prntscr.com/8sya9d | Fixed | https://digitalpfizer.atlassian.net/browse/PUVTMM-364 https://digitalpfizer.atlassian.net/browse/PUVTMM-384 |  | No
[7 empty] | Remove it after review |  |  |  |  | No
11 | Live Streamed Events
| oMZVPsEH9YB - Kulu ID | Arthur | 2016-07-09 | No | H | S | Observe existing page with webinar, check translation, pay attention to all non custom items you see during the testing (translation in popups, messages, email notifications) | All non custom items should be properly translated | Pass |  |  | No
| Bugfix: MHPE-659 BUG MD-915 KuluValley module not creating thumbnail directory | Arthur | 2016-07-09 | No | H | S | Observe just created page with webinar unser admin for error mesages | The following error should not appear - http://prntscr.com/8sya9d | Fixed | https://digitalpfizer.atlassian.net/browse/PUVTMM-364 |  | No
| Bugfix: MHPE-774 L3 - ZEND62322 - Issue with button borders | Arthur | 2016-07-09 | No | H | S | Observe just created page, register for webinar with common_user and check if there are borders around the lonks and inside the popups | There should not be any borders | Fixed | https://digitalpfizer.atlassian.net/browse/PUVTMM-364
[7 empty] | Remove it after review |  |  |  |  | No
12 | NewsCred Articles
| 2.6 News Article Page Template banner Enhancement in 2.7- UI change is contained to only existing news article content pages. Default unless otherwise instructed will be blue colour block News Article Page Template image Enhancement in 2.7 - Image re-sized automatically. New imagery not required | Arthur | 2016-07-09 | No | H | S | Create NewsCred Articles Observe created page with article | Article image is not displayed when Brand image is chosen - http://prntscr.com/bn3tgs When Brand image is not uploaded and default blue banner is displayed - article image is displayed - http://prntscr.com/bn3wo5 It is expected behavior | Fixed | https://digitalpfizer.atlassian.net/browse/PUVTMM-366 |  | No
|  | Arthur | 2016-07-09 | No | H | S | Check that NewsCred Articles is displayed at the correct places (in news list, under category, as one news, on home page if was promoted) | NewsCred Articles should be displayed. Confirm only Articles published within ${period} are displayed on News Articles NewsCred should be displayed on home page and News pages. | Pass |  |  | No
|  |  |  | No | H | S | Remove it after review |  |  |  |  | No
| Bugfix: MHPE-774 L3 - ZEND62322 - Issue with button borders | Arthur | 2016-07-09 | No | H | S | Go to News archive and check if there is border on search button for News | There should not be any borders | Pass
13 | Quick Poll
|  | Arthur | 2016-07-09 | No | H | S | Login as a admin or content editor Create a content using "HCP Poll: Quick Poll" content type. | Quick Poll should work as expected. Quick Polls can be created by admin user and includes: radio buttons, checkboxes Can embed quick polls into: Portal home page, Microsite landing pages, Microsite content pages, News Article pages, Support and Services content pages, Webinar pages, eDetail pages. Confirm Authenticated user can submit quick poll. Quick poll response will display aggregate data, rather than a thank you message. | Pass |  |  | No
| Bugfix: MHPE-759 L3 - HCP Portal 2.7 Bug - Polls do not work properly on 2.7 | Arthur | 2016-07-09 | No | H | S | Submit poll and check if it detect the votes cast. | You should be able to see the votes cast on thank you screen as auth user and anon. Also under admin under polls settings. | Pass |  |  | No
| Hotfix: MHPE-724 / PFHCP-942 / CN#36743 All HCP 2.6 ¦ HCP Portal v2.6 Global Issue: JS Error on home page related to poll | Arthur | 2016-07-09 | No | H | S | Proceed to Home page and pages with the polls, open firebug and click on console tab, reload page Observe that there is no JS error on home page for anonymous users generated by the poll module | No JS errors on home page for anonymous users generated by the poll module; Home hage should not be broken. | Pass |  |  | No
[7 empty] | Remove it after review |  |  |  |  | No
14 | Customer feedback
|  | Arthur | 2016-07-09 | No | H | S | Login as a admin or content editor Create a content using "HCP Poll: Customer Feedback" content type. | Polling: Customer feedback should work Admin user should be able to create Customer Feedback Polls. Verify additional field can be added to display on front end or hidden by admin (detailed feedback field). Admin can define a question type that appears on the front end. Theming matches the rest of HCP Portal Customer Feedback polls and be embedded into: Portal home page, Microsite landing page, News Article pages, Support and Services content pages, Webinar pages, eDetail pages, internal listing/landing pages. Anonymous user should see: Feedback poll block asking user to login to vote. Authenticated user can see poll as expected. Authenticated user can complete and submit poll and see Thank you message. | Pass |  |  | No
| Hotfix: PFHCP-854 Issue with re-ordering options in poll feature | Arthur | 2016-07-09 | No | H | S | You would see in the created content the options are listed | Customer wants this to be displayed in the following order by default: Yes No Maybe | Fixed | https://digitalpfizer.atlassian.net/browse/PUVTMM-367 |  | No
15 | The rest Hot-Fixes
| Bugfix: MHPE-713 PFHCP-951 CN#37279 High HCP Portal Global ¦ References do not work as expected in 2.6 | Arthur | 2016-07-09 | No | H | S | Log in as admin 1. Create test reference - http://prntscr.com/a3xn0y 2. Create test HCP Article with this reference http://prntscr.com/a3xnnt NOTE: brand on a article and on a reference page should be the same 3. Log in as GRV user and check created article with created reference | References should work as expected | Pass |  |  | No
| Bugfix: MHPE-728 PFHCP-981 CN#39977 HCP Critical pfizerpro.dk :deploy page not working on DK portal Dev3 instance | Arthur | 2016-07-09 | No | H | S | Clear deployment plans on Admin -> Structure -> Deploy (/admin/structure/deploy) - http://prntscr.com/9v29em Run Brand feeds import (Admin -> Config -> HCP Portal -> XREF Refresh (/admin/config/hcp/xref) - http://prntscr.com/9v29ru, http://prntscr.com/9v2a0g Find any brand which doesn't have content (has only redirection to PDF) (it is easy using /products page) - http://prntscr.com/9v2af2, http://prntscr.com/9v2b1c Create and publish HCP Product page for this brand - http://prntscr.com/9v2c1v Create and publish HCP Indications page for this brand - http://prntscr.com/9v2cdc Run Brand feeds import - http://prntscr.com/9v2dk6 Observe deleted redirects in deployment plans (admin/structure/deploy) - http://prntscr.com/9v2e5l. Also there are related watchdog messages on Admin -> Reports -> Recent log message - http://prntscr.com/9v2fjc http://prntscr.com/9v2e5l http://prntscr.com/9v2eg7 http://prntscr.com/9v2ew5 | No errors or any other issues should appear | Pass |  |  | No
| Hotfix: PFHCPCCLI-81 - Live Event - Reduce Address field (field_hcp_event_address) from a full address field to display only town and county (state). Due to limitations in addressfield v1.1 a preprocess has had to be used to remove the country from the field. | Arthur | 2016-07-09 | No | H | S | Check address block in existing Live events or create new one | Address field should be reduced (field_hcp_event_address) from a full address field to display only town and county (state). Due to limitations in addressfield v1.1 a preprocess has had to be used to remove the country from the field. Address block should look like on the left side window diplayed on the screenshot - http://prntscr.com/bgdykx | Pass |  |  | No
16 | Customization URLs translation
| HotFix: MHPE-745 Make all the URLs in HCPP Translatable Only for Norway, Netherlands and Austria markets | Arthur | 2016-07-09 | No | H | S | Go to /admin/config/search/path and check existing URLs related to products and medical conditions section. | They should be translated this way: condition -> medisinsk-tilstand product -> legemiddel If they are not translated so they should redirect to new translated URL (Check randomly if exist) |  |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Create the following node types and Check URL: |  |  |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | HCP Medical conditions |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | HCP Products |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Create the folloving node types related to some product and check URL: |  |  |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | HCP Article |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | OnDemand webinar |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Live Webinar |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Live Event |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | NewsCread |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | eDetail |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | HCP Indications |  | Pass |  |  | No
|  |  |  | No | H | S | Create the folloving node types related to some medical condition and check URL: |  |  |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | HCP Article |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | OnDemand webinar |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Live Webinar |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Live Event |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | NewsCread |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | eDetail |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | HCP Indications |  | Pass |  |  | No
17 | Omnichure testing/Report
| Reffer to the "Onmiture testing" tab | Arthur | 2016-07-09 | No | H | S | Omniture variables check | Variables should be correct and linked to the paths/clicks - see attached required Omniture testing Tab need to verify actions are recorded in the Market-specific site analytics suite. Reffer to the "Omnichure testing" tab for the details | Pass |  |  | No
18 | Content clean up
|  | Arthur | 2016-07-09 | No | H | S | Clear deployment plans on Admin -> Structure -> Deploy (/admin/structure/deploy) - http://prntscr.com/9v29em |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Cancel FFW-Content user account and choose delete all account created by this user |  | Pass |  |  | No
|  | Arthur | 2016-07-09 | No | H | S | Observe the site, make sure all test content is removed |  | Pass |  |  | No
For additional rows please insert above this line. Do not change or delete rows below this line
[8 empty] | Pass Count | 66
[8 empty] | Failed Count | 0
[8 empty] | Not Executed Count | 1
[8 empty] | Skipped Count | 0
[5 empty] | Criticality/ Severity (H, M, L) | Rigor of Verification (I, S, M) |  |  |  | Pass, Fail, or Not Executed |  | Evidence Included for Intensive or Standard test cases? (Yes or No)
[5 empty] | H | I |  |  |  | Pass |  | Yes
[5 empty] | M | S |  |  |  | Fail |  | No
[5 empty] | L | M |  |  |  | N/A
Skipping