## Checklist
Deployment Checklist for: Netherlands				Platform	7.x-hcp-2.7.7	Updated:		9/13/2016	Martin Malovanets	Target MTP date:
	HCP 2.7					Production:		URL	www.pfizerpro.nl	Stage:	pfpfpronlstg.prod.acquia-sites.com (2.6.9)
								Project Team POC	Project Team	Dev3	pfpfpronldev3.prod.acquia-sites.com (2.6.9)
								L3 Team POC	L3 Team	Dev5	pfpfpronldev5.prod.acquia-sites.com (2.7.7)
								Content Team POC	Content Team	Latest Code	dev5
								Pfizer BT POC	BT	Latest Content
								Support POC	HCP Support
#	Group	Item	Category	Timeframe Prior to MTP (days)?		Done?	Support Comment	Owner	Date Complete	Confirmed By	Notes
1	General	If site is Soft Launced?					Please provide input	HCP Support
2	General	If market solft launced, Has MTP package received from Project team?					Please provide input	HCP Support
3	General	On which enviroemnt is the latest code residing						L3 Team
4	General	On which environment is the latest content residing						Content Team
5	General	Are CPE/STG/PROD having same platform and HCP subplatform?				No		HCP Support	9/13/2016	Martin Malovanets
6	General	Are there any open Zendesk tickets for this portal?				Yes		HCP Support	9/13/2016	Martin Malovanets	No zendesk tickets related to this upgrade that our team is aware of
7	SDLC	Has a Compliance Risk Profile (CRP) & a CMDB record been generated? https://docs.digitalpfizer.com/sdlc-documentation/cmdb-iprm	Security	30				Project Team
8	SDLC	Has the translation template been completed by the market?		Prior to MTP		N/A	Why is this NA, please provide the details.	HCP Support	9/13/2016	Martin Malovanets
9	DNS	Verify the domain name is secured and using a standard Pfizer name server. http://www.whois.com or other in-market service	DNS	ASAP				BT
10	Security	Is SSL certificate configured for primary domain. (Any page that captures user information needs to be on SSL)	SSL	15		N/A	Why is this NA, please provide the details.	HCP Support	9/13/2016	Martin Malovanets	Site is live
11	Metrics	Is Omniture Report suite configured?		15		Yes		HCP Support			Test cases and report provided - Page and Features
12	Acquia	Check that the production environment has 160MB of APC memory set / https://www.pfpfproXX.prod.acquia-sites.com/ACQUIA_MONITOR Raise a support ticket if not to get this fixed.		15		N/A	Can you please check this from Global support ? Ideally this information should be shared with HCP support at the time of transition	HCP Support	9/13/2016	Martin Malovanets	We don’t have access to this anymore -
13	Acquia	Confirm with BT Support that system CRON is enabled on production to run every 15 minutes (4 times an hour)		7		N/A	Why is this NA, please provide the details.	HCP Support	9/13/2016		Site is live
14	Custom	Have any custom code been written by Project Team? Is code reviewed?	-	7		Yes	What code changes were done, please share the details ?	HCP Support	9/13/2016		Coder report provided
15	Custom	Have any custom code been written by L3 support team? Is code reviewed?	-	7				L3 Team
16	SDLC	Have you reviewed JIRA for open tickets? https://smscvt.atlassian.net/		7		Yes		HCP Support	9/13/2016		https://digitalpfizer.atlassian.net/browse/PUVTMM-276
17	Custom	Has Project Team run the Coder Report on custom modules/code and upload these reports to the deployment documents folder?	Deploy	5		Yes		HCP Support	9/13/2016		Attached
18	Custom	Has L3 Team run the Coder Report on custom modules/code and upload these reports to the deployment documents folder?	Deploy	5				L3 Team
19	Janrain	Have you notified the Janrain team of Production deployment schedule (email at least one week in advance)?	GRV	7		N/A		HCP Support			Site is live
20	Janrain	Have you confirmed that final, approved GRV screens have been deployed to GRV Production (Amazon)? https://github.com/pfizer/janrain_capture_screens	GRV	5		N/A	Please provide input	HCP Support	9/13/2016	Martin Malovanets	Site is live
21	Kuluvalley	Is pfizer_kuluvalley enabled? Has the Kulu Valley player configurations for DEV been confirmed and added to local.settings.php?	Kulu Valley	5		Yes		HCP Support	9/13/2016	Martin Malovanets
22	Kuluvalley	Has the Kulu Valley player configurations for Stage and Production been confirmed and added to local.settings.php?	Kulu Valley	5		Yes		HCP Support	9/13/2016	Martin Malovanets
23	Janrain	Is pfizer_grv enabled?		5		Yes		HCP Support
24	Janrain	Have you requested the Production GRV configuration information and verified the correct settings in the local.settings.php file?		5		Yes	No separate janrain settings for Dev5 . Please provide the reason for this deviation.	HCP Support		Martin Malovanets	Site is live. GRV functionality not affected
25	Pitcher	(2.3) Has Pitcher Client creation been requested from BT-SUPPORT? Has Pitcher been enabled ( pfizer_pitcher ) and configured for site?		5		N/A	Why is this NA, does Netherland do not have pitcher? Please provide input	HCP Support	9/13/2016	Martin Malovanets
26	Pitcher	(2.3) If eDetails is enabled (pfizer_hcp2_edetail pfizer_hcp2_edetail_pitcher pfizer_hcp2_edetail_perms) verify that platform is 2.3.3 or greater		5		N/A	Does Netherland HCP do not have eDetail.	HCP Support	9/13/2016	Martin Malovanets
27	Branding	(2.3.3) Remove pfizer_pro_product_branding module if it exists ( this feature now incorporated into 2.3.3)		5		N/A		HCP Support	9/13/2016	Martin Malovanets	Not present
28	Branding	Has custom branding S3 host been configured for each of the environments(Dev/Stg/Prod) in Local.settings.php $conf[pfizer_pro_s3_bucket]?		5				L3 Team
29	Content	Verify "Full HTML with Scripts" Text Format for Brightcove. /admin/config/content/formats		5		Yes		HCP Support	9/13/2016	Martin Malovanets
30	Performance	Confirm with BT Support that Acquia has enabled "Varnish through SSL" option.		5		Yes		HCP Support	9/13/2016	Martin Malovanets	Currently enabled in Prod
31	Janrain	If integrating with 3rd party validation, insure production domain name has been whitelisted with Janrain prior to launch, / Email (DL-BT-DIGITALMARKETING@pfizer.com) to confirm.	GRV	5		N/A	Why is this NA, please provide the details.	HCP Support
32	Content	Has the portal "demo" content been removed and un-published from the site and Brands feed?		5				Content Team
33	Migration	Do we have PMI (PfizerMedInfo) built for the market in question? And if so, is there interconnectivity of the authentication solution in place?	-	5				BT
34	Migration	If preexisting site, has Pfizer Connect user data migration been completed for this market to the new GRV solution?	GRV	5				BT
35	SDLC	Has the SDLC Deployment Document been completed for Code Changes (must be sent with MTP documentation prior to the deployment)?	MTP	Min. 3 days prior to MTP				L3 Team
36	SDLC	Has the SDLC Deployment Document been completed for Content Changes (must be sent with MTP documentation prior to the deployment)?	MTP	Min. 3 days prior to MTP				Content Team
37	SDLC	Has the business unit sent approval email? Include approval email in Deployment Plan documentation.	MTP	Min. 3 days prior to MTP				BT
38	SDLC	Have you scheduled the MTP with the Support Team (email to DL-BT at least 3 days in advance of deployment date)?	MTP	Min. 3 days prior to MTP		N/A		HCP Support
39	SDLC	Has the BT Solutions Center sent approval email? Include approval email in Deployment Plan documentation.	MTP	Min. 3 days prior to MTP				BT
40	Janrain	Confirm GRV configuration information for Production is included in the Deployment Plan.	GRV	Min. 3 days prior to MTP		Yes		HCP Support	9/13/2016	Martin Malovanets
41	Custom	Create changelog.txt in the GitHub directory and fill in details of what has been customised whilst deploying this Portal.		Prior to MTP				L3 Team
42	Janrain	Delete all GRV test accounts, disable all non-essential Drupal accounts		Prior to MTP		Yes		HCP Support	9/13/2016	Martin Malovanets	user table will be skipped during MTP
43	Custom	pfizer_pro_product_branding - If used verify that Brands.css and Brands.js files are moved into production S3 bucket - https://github.com/pfizer/pfizerpro-global-s3		Prior to MTP		N/A	Please provide input	HCP Support	9/13/2016	Martin Malovanets
44	Kuluvalley	If KuluValley is enabled have the Webinar email settings been configured? /admin/config/system/pfizer_hcp/webinar		Prior to MTP		Yes		HCP Support
45	Brightcove	Has the BrightCove configuration for Production been confirmed and added to local.settings.php?	BrightCove	Prior to MTP		Yes		HCP Support	9/13/2016	Martin Malovanets
46	Language	Has the site been translated into market's language(s). Are Language settings correctly set to support single or multiple languages.	Deploy	Prior to MTP		Yes		HCP Support	9/13/2016	Martin Malovanets
47	SDLC	Have you read & followed the Pfizer technical standard guides: Drupal Custom	Deploy	Prior to MTP		Yes		HCP Support	9/13/2016	Martin Malovanets
48	SDLC	Have you read & followed the Pfizer technical standard guides: Drupal Custom	Deploy	Prior to MTP				L3 Team
49	Security	Has the security test been completed and approved? Include approval email in Deployment Plan documentation.	Security	Prior to MTP				L3 Team
50	Security	Has the security test been completed and approved? Include approval email in Deployment Plan documentation.	Security	Prior to MTP				L3 Team
51	Security	Have you completed the securepages configuration? Have you confirme that /user and /admin pages are using SSL.	Deploy	Prior to MTP		N/A	Please provide input	HCP Support	9/13/2016	Martin Malovanets	We didn’t configure any since market is live
52	Security	secure cookies have been enabled? $conf['https'] = FALSE;	Deploy	Prior to MTP		Yes		HCP Support	9/13/2016	Martin Malovanets
53	Content	Have you removed and/or updated the favicon.ico	Omniture / IM	Prior to MTP				Content Team
54	Security	Ensure that anonymous users do not have elevated permissions. Make sure anonymous user does not have permission to create account on sites (unless its business requirement). admin/config/people/accounts	Deploy	Prior to MTP				L3 Team
55	Security	Have you verified configuration for new Drupal pages. Make sure anonymous users DO NOT have admin rights to view unpublished, create, or update nodes/pages. /admin/people/permissions	Deploy	Prior to MTP				L3 Team
56	Performance	Has Drupal and Varnish cache been enable on site? Please refer to Improving website performance: https://docs.digitalpfizer.com/drupal-custom-development/improving-website-performance	Deploy	Prior to MTP		Yes		HCP Support	9/13/2016	Martin Malovanets
57	Metrics	Confirm Omniture / Web Standards module is enabled (pfizer_webstandards_hcp2) and configurations are in local.settings.php. Review the actual suite in SiteCatalyst to see if the events are indeed firing correctly and the correct suite name is being used on dev and prod. Ensure any dev settings have been removed or deprecated so they do not impact production. Check ALL specific events, e.g. registration, event registration etc.	Omniture / IM	Prior to MTP AND Day of MTP				L3 Team
58	Performance	Have routes for vanity urls been created, including non-www url to the primary domain? (Platform team will procure SSL for only for primary domain.) Redirect for both http and https. apache_custom.conf	DNS	Prior to MTP		Yes		L3 Team
59	Security	Have reoutes been created to route user/login, user/password, and user/register to /login?		Prior to MTP		Yes		HCP Support	9/13/2016	Martin Malovanets	We didn’t configure any since market is live
60	Content	Is the Web service connectivity (ie: Brands feed) configured as per the required environments in Local.settings.php (stage/production) ?	-	Prior to MTP		Yes		HCP Support	9/13/2016	Martin Malovanets
61	Security	Verify that Devel and Backup & Migrate have been disabled on production		Prior to MTP		Yes		HCP Support
62	Content	Verify that Deploy is enabled/disabled per market requirements.	DNS	Prior to MTP		Yes		HCP Support			Deploy module enabled
63	Metrics	Do you need a specific page (other than the home page) to be added to the support monitoring solution?	Support	Min. 3 days prior to MTP				BT
64	Custom	Confirm Behat tests completed and passed.	-	N/A				L3 Team
65	SDLC	Confirm production deployment Git tag.	Deploy	Day of MTP				HCP Support
66	SDLC	Has the approved site been pushed to stg for MTP?		Min. 3 days prior to MTP				HCP Support
67	General	Are amazon S3 files(CSS/JS/Assets) moved from Dev to Stg bucket?				N/A		HCP Support	9/13/2016	Martin Malovanets
68	SDLC	Have you completed the KT Checklist and documentation?		N/A		Yes		HCP Support	9/13/2016	Martin Malovanets
69	SDLC	Have you scheduled the KT Meeting?		N/A				HCP Support
70	Janrain	IF moving GRV into production for the first time, advise Chris L so that he can enable production GRV Admin Tool.	SSL	Day of MTP		N/A		HCP Support
71	Content	Prior prod launch check with Oleg to ask if the prod domains were whitelisted for fontdeck.com		Prior to MTP		N/A		HCP Support	9/13/2016	Martin Malovanets	Site is live n/a
72	Acquia	Make sure $_ENV is used instead of $_SERVER in local.settings.php		Prior to MTP		Yes		HCP Support	9/13/2016	Martin Malovanets
73	Security	Make sure your deployment instruction have "Allow login" set to "YES" since this is a requirement for GRV		Day of MTP		Yes		HCP Support	9/13/2016	Martin Malovanets
74	Performance	Is Memcache configured correctly within local.settings.php?		Prior to MTP		Yes		HCP Support	9/13/2016	Martin Malovanets
75	Performance	Is the memory_limit set to at least 512 in local.setting.php for all environments		Prior to MTP		Yes		HCP Support	9/13/2016	Martin Malovanets
76	GRV	GRV Admin Tool Onboarding for a country business person, who will be managing GRV users for the country		Prior to MTP				BT
77	General	Anonymous user shouldn’t see the home and product pages						L3 Team

## BT Questions
BT need to respond to below queries before Go Live
Verify the domain name is secured and using a standard Pfizer name server. http://www.whois.com or other in-market service
Do we have PMI (PfizerMedInfo) built for the market in question? And if so, is there interconnectivity of the authentication solution in place?
If preexisting site, has Pfizer Connect user data migration been completed for this market to the new GRV solution?
Has the business unit sent approval email? Include approval email in Deployment Plan documentation.
Has the BT Solutions Center sent approval email? Include approval email in Deployment Plan documentation.
Do you need a specific page (other than the home page) to be added to the support monitoring solution?
GRV Admin Tool Onboarding for a country business person, who will be managing GRV users for the country

## L3 Team Questions
L3 need to respond to below queries before MTP
On which enviroemnt is the latest code residing
Have any custom code been written by L3 support team? Is code reviewed?
Has L3 Team run the Coder Report on custom modules/code and upload these reports to the deployment documents folder?
Has custom branding S3 host been configured for each of the environments(Dev/Stg/Prod) in Local.settings.php $conf[pfizer_pro_s3_bucket]?
Has the SDLC Deployment Document been completed for Code Changes (must be sent with MTP documentation prior to the deployment)?
Create changelog.txt in the GitHub directory and fill in details of what has been customised whilst deploying this Portal.
Have you read & followed the Pfizer technical standard guides: Drupal Custom
Has the security test been completed and approved? Include approval email in Deployment Plan documentation.
Ensure that anonymous users do not have elevated permissions. Make sure anonymous user does not have permission to create account on sites (unless its business requirement). admin/config/people/accounts
Have you verified configuration for new Drupal pages. Make sure anonymous users DO NOT have admin rights to view unpublished, create, or update nodes/pages. /admin/people/permissions
Confirm Omniture / Web Standards module is enabled (pfizer_webstandards_hcp2) and configurations are in local.settings.php. Review the actual suite in SiteCatalyst to see if the events are indeed firing correctly and the correct suite name is being used on dev and prod. Ensure any dev settings have been removed or deprecated so they do not impact production. Check ALL specific events, e.g. registration, event registration etc.
Have routes for vanity urls been created, including non-www url to the primary domain? (Platform team will procure SSL for only for primary domain.) Redirect for both http and https. apache_custom.conf
Confirm Behat tests completed and passed.
Anonymous user shouldn’t see the home and product pages