## Omniture Testing
|  | RS Title | Portugal HCP Portal Dev | HCP Portal
|  | URL | pfpfproptdev5.prod.acquia-sites.com
User Exp. | Event / location | Img Req. Type | RSID 1 | RSID 2 | Issue / Observation (if any) | Test Status (PASS, FAIL, N/A) | 2016-08-25
Flow | Homepage | onLoad | pfizerpfizerhcpportugalstaging | pfizerglobalimdevelopment | Event 7 (should work also for the rest pages as for anon user and for authorized user also) | Pass | http://prntscr.com/ca8r3r
Use Case # 1 | Registration Initiated | Onclick | pfizerpfizerhcpportugalstaging | pfizerglobalimdevelopment | Event8: Registration Initiated Action – event8 should be triggered from the request having correct link name. | Pass | http://prntscr.com/ca8rld
Use Case # 2 | Registration Completed | Onclick | pfizerpfizerhcpportugalstaging | pfizerglobalimdevelopment | Event9 – Registration Completed Action – event9 should be triggered from the registration form submitting having correct link name. | Pass | http://prntscr.com/ca8ttf
Use Case # 3 | Login Initiated | Onclick | pfizerpfizerhcpportugalstaging | pfizerglobalimdevelopment | Event36: Login Initiated - should be requested Action – event36 should be triggered from the request having correct link name. | Pass | http://prntscr.com/ca8u5k
Use Case # 4 | Login Complete | Onclick | pfizerpfizerhcpportugalstaging | pfizerglobalimdevelopment | Event37 – Login Completed Should be triggered for login form submiting. | Pass | http://prntscr.com/ca8yl2
Use Case # 5 | File Download | Onclick | pfizerpfizerhcpportugalstaging | pfizerglobalimdevelopment | Event4, link_d | N/A
Use Case # 6 | Exit Link | Onclick | pfizerpfizerhcpportugalstaging | pfizerglobalimdevelopment | Link_e | Pass | http://prntscr.com/ca95md
Use Case # 7 | Video Tracking | Onclick | pfizereudmawebinardev | pfizereudmawebinardev | event10,event19,event20,event27,event36 Check Webinars video | N/A | Webinar videos are not displayed because of some KV global issues
Use Case #8 | Customer Feedback Poll - Complete | Onclick | pfizerpfizerhcpportugalstaging | pfizerglobalimdevelopment | Event41, Link type "lnk_o" Link name "content_poll" Check that In Adobe Analytics it must be possible to track the number of users who successfully complete a Customer Feedback Poll. - No events appears for any market at the moment | N/A
Instructions
Ensure you have the market-specific Omnniture suite name and access to it on the Omniture Adobe Analytics site analytics suite.
Create a tab for each use case listed above
Enter details on each tab as noted in example on:https://smscvt.atlassian.net/browse/MD-809
Test actions on the website and validate they are logged on the market-specific site analytics suite
Take screenshots of findings
Test needs to be done during development QA AND as part of MTP validation.
Submit completed report (including pass and fail information) to PM or upload to QA ticket.
Generate Omniture report in https://sc2.omniture.com and upload to the ticket