## Checklist
Deployment Checklist for: <Market Name> |  |  |  | Platform | 7.x-2.4.24 | Updated: | <Date> |  | Target MTP date: | <Date>
| HCP VER | <HCP Platform Version> |  | Subplatform | 7.x-hcp-2.6.8 | Production: | URL | <URL> | Stage:
[7 empty] | Project Team POC |  | Dev3
[7 empty] | L3 Team POC |  | Latest Code
[7 empty] | Content Team POC |  | Latest Content
Pfizer BT POC
Support POC
# | Group | Item | Category | Timeframe Prior to MTP (days)? |  | Done? | Owner | Date Complete | Comment | Instructions
1 | General | Setup Self Service and Block all user accounts on Drupal, having Drupal Role(content admin, content editor, admin etc), before moving DB from Dev3 to Stage except Deploy Admin users | User Access | After Content Freeze |  |  | HCP Support |  |  | Unauthorized users deleted on dev3 and stage
2 | GRV | Check GRV settings while moving Dev3 to Stage. GRV values changes for Dev and Stage | GRV | As soon As Heads up for Go Live or Content Freez Recived |  |  | HCP Support
3 | Security | Cross Frame Scripting issue must be addressed before initiating Security Scan. | Security | Before Security Scan |  |  | HCP Support |  |  | Go to https://pfpfprofrdev3.prod.acquia-sites.com/admin/config/system/seckit Change X-Fram Options from Same-Oroigin to Deny X-Frame-Bust methods: Sirdarckcat method Then raise Security Scan, this helps to get clean security scan with no high issue. Once done with Security Scan, do revert Deny to Same Origin for Dev and Stage
4 | General | If site is Soft Launced? | Info | N/A |  |  | HCP Support |  |  | Make sure to visi Acquia Prod domain eg: https://pfpfprofr.prod.acquia-sites.com/ And Make sure Site Guard is enabled
5 | General | If market solft launced, Has MTP package received from Project team? | Info | Verify as your recived Deployment Kit from Projet Team |  |  | HCP Support |  |  | Verify : Omniture Report, Clean Coder Report, MTP Document (i.e. SDLC Doc) BT Approval
6 | General | On which enviroemnt is the latest code residing | Code | After Code Freez |  |  | HCP Support |  |  | After code Freez, all new changes has to be merged on Dev3 by raising PR by Project team to HCP Support Team as per Region.
7 | General | On which environment is the latest content residing | Content | After Content Freez |  |  | HCP Support |  |  | Content Team should give ocnfirmation on content Freez: 1. This includes any S3 CSS/JS changes by Content 2. Content Admin work etc 3. Any open tickets related to content
8 | General | Are CPE/STG/PROD having same platform and HCP subplatform? | Config | Before Merging Dev3 to Stage and moving to Prod |  |  | HCP Support
9 | General | Are there any open Zendesk tickets for this portal? | Info | Before Merging Dev3 to Stage and moving to Prod |  |  | HCP Support |  |  | #64800, #64886, #64479
10 | SDLC | Has a Compliance Risk Profile (CRP) & a CMDB record been generated? https://docs.digitalpfizer.com/sdlc-documentation/cmdb-iprm | Info | 30 |  |  | HCP Support |  |  | As per MCG doc : Verify CMDB on http://btsmweb.pfizer.com/ and http://btsmweb.pfizer.com/
11 | SDLC | Has the translation template been completed by the market? | Translation | Prior to MTP |  |  | HCP Support
12 | DNS | Verify the domain name is secured and using a standard Pfizer name server. http://www.whois.com or other in-market service | DNS | ASAP | Before MTP |  | HCP Support
13 | Security | Is SSL certificate configured for primary domain. (Any page that captures user information needs to be on SSL) | SSL | 15 | Before MTP |  | HCP Support |  |  | Verify it with DL-BT-Team
14 | Metrics | Is Omniture Report suite configured? | Omniture / IM | 15 | As Code and content Freez happens |  | HCP Support
15 | Acquia | Check that the production environment has 160MB of APC memory set https://www.pfpfproXX.prod.acquia-sites.com/ACQUIA_MONITOR Raise a support ticket if not to get this fixed. | Env | 15 |  |  | HCP Support
16 | Acquia | Confirm with BT Support that system CRON is enabled on production to run every 15 minutes (4 times an hour) | Config | 7 | During MTP |  | HCP Support
17 | Custom | Have any custom code been written by Project Team? Is code reviewed? | Code | 7 |  |  | HCP Support
18 | Custom | Have any custom code been written by L3 support team? Is code reviewed? | Code | 7 |  |  | HCP Support
19 | SDLC | Have you reviewed JIRA for open tickets? https://smscvt.atlassian.net/ | Info | 7 |  |  | HCP Support
20 | Custom | Has Project Team run the Coder Report on custom modules/code and upload these reports to the deployment documents folder? | Deploy | 5 |  |  | HCP Support
21 | Custom | Has L3 Team run the Coder Report on custom modules/code and upload these reports to the deployment documents folder? | Deploy | 5 |  |  | HCP Support
22 | Janrain | Have you notified the Janrain team of Production deployment schedule (email at least one week in advance)? | GRV | 7 |  |  | HCP Support
23 | Janrain | Have you confirmed that final, approved GRV screens have been deployed to GRV Production (Amazon)? https://github.com/pfizer/janrain_capture_screens | GRV | 5 |  |  | HCP Support
24 | Kuluvalley | Is pfizer_kuluvalley enabled? Has the Kulu Valley player configurations for DEV been confirmed and added to local.settings.php? | Config | 5 |  |  | HCP Support
25 | Kuluvalley | Has the Kulu Valley player configurations for Stage and Production been confirmed and added to local.settings.php? | Config | 5 |  |  | HCP Support
26 | Janrain | Is pfizer_grv enabled? | GRV | 5 |  |  | HCP Support
27 | Janrain | Have you requested the Production GRV configuration information and verified the correct settings in the local.settings.php file? | GRV | 5 |  |  | HCP Support
28 | Pitcher | (2.3) Has Pitcher Client creation been requested from BT-SUPPORT? Has Pitcher been enabled ( pfizer_pitcher ) and configured for site? | Config | 5 |  |  | HCP Support
29 | Pitcher | (2.3) If eDetails is enabled (pfizer_hcp2_edetail pfizer_hcp2_edetail_pitcher pfizer_hcp2_edetail_perms) verify that platform is 2.3.3 or greater | Config | 5 |  |  | HCP Support
30 | Branding | (2.3.3) Remove pfizer_pro_product_branding module if it exists ( this feature now incorporated into 2.3.3) | Config | 5 |  |  | HCP Support
31 | Branding | Has custom branding S3 host been configured for each of the environments(Dev/Stg/Prod) in Local.settings.php $conf[pfizer_pro_s3_bucket]? | Config | 5 |  |  | HCP Support
32 | Content | Verify "Full HTML with Scripts" Text Format for Brightcove. /admin/config/content/formats | Config | 5 |  |  | HCP Support
33 | Performance | Confirm with BT Support that Acquia has enabled "Varnish through SSL" option. | ENV | 5 | During MTP |  | HCP Support
34 | Janrain | If integrating with 3rd party validation, insure production domain name has been whitelisted with Janrain prior to launch, Email (DL-BT-DIGITALMARKETING@pfizer.com) to confirm. | GRV | 5 |  |  | HCP Support
35 | Content | Has the portal "demo" content been removed and un-published from the site and Brands feed? | Content | 5 |  |  | HCP Support
36 | Migration | Do we have PMI (PfizerMedInfo) built for the market in question? And if so, is there interconnectivity of the authentication solution in place? | GRV | 5 |  |  | HCP Support
37 | Migration | If preexisting site, has Pfizer Connect user data migration been completed for this market to the new GRV solution? | GRV | 5 |  |  | HCP Support
38 | SDLC | Has the SDLC Deployment Document been completed for Code Changes (must be sent with MTP documentation prior to the deployment)? | MTP | Min. 3 days prior to MTP |  |  | HCP Support
39 | SDLC | Has the SDLC Deployment Document been completed for Content Changes (must be sent with MTP documentation prior to the deployment)? | MTP | Min. 3 days prior to MTP |  |  | HCP Support
40 | SDLC | Has the business unit sent approval email? Include approval email in Deployment Plan documentation. | MTP | Min. 3 days prior to MTP |  |  | HCP Support
41 | SDLC | Have you scheduled the MTP with the Support Team (email to DL-BT at least 3 days in advance of deployment date)? | MTP | Min. 3 days prior to MTP |  |  | HCP Support
42 | SDLC | Has the BT Solutions Center sent approval email? Include approval email in Deployment Plan documentation. | MTP | Min. 3 days prior to MTP |  |  | HCP Support
43 | Janrain | Confirm GRV configuration information for Production is included in the Deployment Plan. | GRV | Min. 3 days prior to MTP |  |  | HCP Support
44 | Custom | Create changelog.txt in the GitHub directory and fill in details of what has been customised whilst deploying this Portal. | MTP | Prior to MTP |  |  | HCP Support
45 | Janrain | Delete all GRV test accounts, disable all non-essential Drupal accounts | GRV | Prior to MTP |  |  | HCP Support
46 | Custom | pfizer_pro_product_branding - If used verify that Brands.css and Brands.js files are moved into production S3 bucket - https://github.com/pfizer/pfizerpro-global-s3 | Config | Prior to MTP |  |  | HCP Support
47 | Kuluvalley | If KuluValley is enabled have the Webinar email settings been configured? /admin/config/system/pfizer_hcp/webinar | Config | Prior to MTP |  |  | HCP Support
48 | Brightcove | Has the BrightCove configuration for Production been confirmed and added to local.settings.php? | Config | Prior to MTP |  |  | HCP Support
49 | Language | Has the site been translated into market's language(s). Are Language settings correctly set to support single or multiple languages. | Deploy | Prior to MTP |  |  | HCP Support
50 | SDLC | Have you read & followed the Pfizer technical standard guides: Drupal Custom | Deploy | Prior to MTP |  |  | HCP Support
51 | SDLC | Have you read & followed the Pfizer technical standard guides: Drupal Custom | Deploy | Prior to MTP |  |  | HCP Support
52 | Security | Has the security test been completed and approved? Include approval email in Deployment Plan documentation. | Security | Prior to MTP |  |  | HCP Support
54 | Security | Have you completed the securepages configuration? Have you confirme that /user and /admin pages are using SSL. | Deploy | Prior to MTP |  |  | HCP Support
55 | Security | secure cookies have been enabled? $conf['https'] = FALSE; | Deploy | Prior to MTP |  |  | HCP Support
56 | Content | Have you removed and/or updated the favicon.ico | Info | Prior to MTP |  |  | HCP Support
57 | Security | Ensure that anonymous users do not have elevated permissions. Make sure anonymous user does not have permission to create account on sites (unless its business requirement). admin/config/people/accounts | Deploy | Prior to MTP |  |  | HCP Support
58 | Security | Have you verified configuration for new Drupal pages. Make sure anonymous users DO NOT have admin rights to view unpublished, create, or update nodes/pages. /admin/people/permissions | Deploy | Prior to MTP |  |  | HCP Support
59 | Performance | Has Drupal and Varnish cache been enable on site? Please refer to Improving website performance: https://docs.digitalpfizer.com/drupal-custom-development/improving-website-performance | Deploy | Prior to MTP | During MTP |  | HCP Support
60 | Metrics | Confirm Omniture / Web Standards module is enabled (pfizer_webstandards_hcp2) and configurations are in local.settings.php. Review the actual suite in SiteCatalyst to see if the events are indeed firing correctly and the correct suite name is being used on dev and prod. Ensure any dev settings have been removed or deprecated so they do not impact production. Check ALL specific events, e.g. registration, event registration etc. | Omniture / IM | Prior to MTP AND Day of MTP |  |  | HCP Support
61 | Performance | Have routes for vanity urls been created, including non-www url to the primary domain? (Platform team will procure SSL for only for primary domain.) Redirect for both http and https. apache_custom.conf | DNS | Prior to MTP |  |  | HCP Support
62 | Security | Have reoutes been created to route user/login, user/password, and user/register to /login? | Config | Prior to MTP |  |  | HCP Support
63 | Content | Is the Web service connectivity (ie: Brands feed) configured as per the required environments in Local.settings.php (stage/production) ? | Config | Prior to MTP |  |  | HCP Support
64 | Security | Verify that Devel and Backup & Migrate have been disabled on production | Config | Prior to MTP |  |  | HCP Support
65 | Content | Verify that Deploy is enabled/disabled per market requirements. | DNS | Prior to MTP |  |  | HCP Support
66 | Metrics | Do you need a specific page (other than the home page) to be added to the support monitoring solution? | Support | Min. 3 days prior to MTP |  |  | HCP Support
67 | Custom | Confirm Behat tests completed and passed. | QA | N/A |  |  | HCP Support
68 | SDLC | Confirm production deployment Git tag. | Deploy | Day of MTP | During MTP |  | HCP Support
69 | SDLC | Has the approved site been pushed to stg for MTP? | MTP | Min. 3 days prior to MTP |  |  | HCP Support
70 | General | Are amazon S3 files(CSS/JS/Assets) moved from Dev to Stg bucket? | MTP |  |  |  | HCP Support
71 | SDLC | Have you completed the KT Checklist and documentation? | MTP | N/A |  |  | HCP Support
72 | SDLC | Have you scheduled the KT Meeting? | MTP | N/A |  |  | HCP Support
73 | Janrain | IF moving GRV into production for the first time, advise Chris L so that he can enable production GRV Admin Tool. | SSL | Day of MTP |  |  | HCP Support
74 | Content | Prior prod launch check with Oleg to ask if the prod domains were whitelisted for fontdeck.com | MTP | Prior to MTP |  |  | HCP Support
75 | Acquia | Make sure $_ENV is used instead of $_SERVER in local.settings.php | Config | Prior to MTP |  |  | HCP Support
76 | Security | Make sure your deployment instruction have "Allow login" set to "YES" since this is a requirement for GRV | MTP | Day of MTP |  |  | HCP Support
77 | Performance | Is Memcache configured correctly within local.settings.php? | ENV | Prior to MTP |  |  | HCP Support
78 | Performance | Is the memory_limit set to at least 512 in local.setting.php for all environments | Config | Prior to MTP |  |  | HCP Support
79 | GRV | GRV Admin Tool Onboarding for a country business person, who will be managing GRV users for the country | GRV | Prior to MTP |  |  | HCP Support
80 | GRV | Review user list . If it has both (pending and validated ) user role then refer Pfizer_GRV_Access and Pfizer_GRV_Janrain_Access module. These modules should be enabled. | GRV | Prior to MTP |  |  | HCP Support |  |  | Refer - Russia Portal…This would require us to test the user validation workflow.
81 | General | Do we need to have home page behind GRV? | GRV | Prior to MTP |  |  | HCP Support |  |  | If dev3 environment has restrictions available for annonymous users then same can be tested/verified on stage
82 | Settings | non-www to www redirection rule must be written in htaccess file. | Config | Day of MTP | During MTP |  | HCP Support |  |  | Refer: https://github.com/pfizer/pfizerprodk/blob/stage/source/deploy/apache_custom.conf RewriteCond %{HTTP_HOST} ^pfizerpro\.dk$ [NC] RewriteRule ^(.*)$ https://www.pfizerpro.dk/$1 [R=permanent,L]
83 | Settings | NewsCred feed should be disabled for Stage and Prod | Config | Prior to MTP |  |  | HCP Support |  |  | Configure and Keep the feed import disabled as default. If business has requested to enable the same then only enable this feed.
84 | Self service | Check self service setting between dev3 and stage by creating a unpublished dummy content on dev3 and moving it to stage using depoy tool | Deploy | Prior to MTP |  |  | HCP Support
85 | Self service | Check self service between stage and prod by creating a unpublished dummy content on stage and moving it to production using depoy tool | Deploy | Day of MTP | Post Launch |  | HCP Support |  |  | Steps to be added in SDLC are: 1. Do login in stage portal as pfizer-admin i.e. uid (1) 2. Go to https://XYZstg.prod.acquia-sites.com/admin/structure/deploy/endpoints/list/next/edit/authenticator and update password and save the page
86 | SDLC | Make sure all the users with privileged users should be deleted from production environment except pfizer-admin and site_admin. | User Access | Prior to MTP | Post Launch |  | HCP Support |  |  | This step should be documented properly in SDLC document
87 | SDLC | Make sure "Allow Login" is set as "Yes". This should be set in SDLC document | MTP | Prior to MTP |  |  | HCP Support |  |  | This is needed so that users do not face 404 while accessing my profile, /user pages

## BT Questions
BT need to respond to below queries before Go Live
Verify the domain name is secured and using a standard Pfizer name server. http://www.whois.com or other in-market service
Do we have PMI (PfizerMedInfo) built for the market in question? And if so, is there interconnectivity of the authentication solution in place?
If preexisting site, has Pfizer Connect user data migration been completed for this market to the new GRV solution?
Has the business unit sent approval email? Include approval email in Deployment Plan documentation.
Has the BT Solutions Center sent approval email? Include approval email in Deployment Plan documentation.
Do you need a specific page (other than the home page) to be added to the support monitoring solution?
GRV Admin Tool Onboarding for a country business person, who will be managing GRV users for the country

## L3 Team Questions
L3 need to respond to below queries before MTP
On which enviroemnt is the latest code residing
Have any custom code been written by L3 support team? Is code reviewed?
Has L3 Team run the Coder Report on custom modules/code and upload these reports to the deployment documents folder?
Has custom branding S3 host been configured for each of the environments(Dev/Stg/Prod) in Local.settings.php $conf[pfizer_pro_s3_bucket]?
Has the SDLC Deployment Document been completed for Code Changes (must be sent with MTP documentation prior to the deployment)?
Create changelog.txt in the GitHub directory and fill in details of what has been customised whilst deploying this Portal.
Have you read & followed the Pfizer technical standard guides: Drupal Custom
Has the security test been completed and approved? Include approval email in Deployment Plan documentation.
Ensure that anonymous users do not have elevated permissions. Make sure anonymous user does not have permission to create account on sites (unless its business requirement). admin/config/people/accounts
Have you verified configuration for new Drupal pages. Make sure anonymous users DO NOT have admin rights to view unpublished, create, or update nodes/pages. /admin/people/permissions
Confirm Omniture / Web Standards module is enabled (pfizer_webstandards_hcp2) and configurations are in local.settings.php. Review the actual suite in SiteCatalyst to see if the events are indeed firing correctly and the correct suite name is being used on dev and prod. Ensure any dev settings have been removed or deprecated so they do not impact production. Check ALL specific events, e.g. registration, event registration etc.
Have routes for vanity urls been created, including non-www url to the primary domain? (Platform team will procure SSL for only for primary domain.) Redirect for both http and https. apache_custom.conf
Confirm Behat tests completed and passed.
Anonymous user shouldn’t see the home and product pages