## Sheet1
Checkpoint | Verification Point | Date Completion | Status | Comment
Coder Report / Code review | Check if coder report is present and if there is any critical warning in coder report. Coder report should be in txt format. | 2016-09-12 | Pass
Deployment checklist | Check if the assets provided has deployment checklist and review if deployment checklist is complete | 2016-09-12 | Fail | Obsevations in Deployment checklist
QA Document | Check of QA sheet is provided as a part of KT docs |  | Fail
Epic Ticket |  | 2016-09-12 | Fail | There are JIRA tickets open - PUVTMM-285, PUVTMM-291, PUVTMM-378, PUVTMM-379
Security Scan Report | generally this is not present at the time of KT, but do mention this to Upgrade PM POC (Pavan / Oleg) |  | Pending
PI Tool Report | Chec in pi.digitalpfizer.com if PI platform check if Pass and Fail | 2016-09-12 | Pass
UAT Signoff | Based on the date provided in upgrade calander |  | Pending
SDLC Document | Check if the SDLC document is present and all details are verified | 2016-09-12 | Fail | 1. Please provide Request Number 2. As per Row #7, Dev5 Platform version is v2.7.6 but as per SDLC document ,platform version of upgraded environment should be 2.7.5. Please verify. 4. Please verify if CMDB id is correct and compliance status is confirmed by solution center owner. 5. Please confirm the Business Owner, BT representative and BT Project Manager. 6. Customer feedback and quick poll details status are in N/A state. 7. In Deployment instructions- Please mention the instructions for moving Amazon S3 buckets for CSS/JS and brand json files from stage to prod. 8. Security approval required. 9. Test cases not provided. 10. Confirm whether we have to skip the tables mentioned in the document.
Omniture Report |  | 2016-09-12 | Fail | Why are event10,event19,event20,event27,event36, event41 not applicable
Market Customization Report | Check for the market level customization done in the portal if any |  | Pending
Dev5 Admin Creds | Check if you are provided with Dev5 admin credentials |  | Pending
Content Team Approval | Get the approval from content team if a live site is getting upgraded. |  | Pending
Dev3 upgrade plan | In case a live site is getting upgraded , please get the clear plan of action for upgradation of Dev3 instance. |  | Pending
Code and content freeze | In case of live markets, please get the timeline for code and content freeze dates and inform the regional market lead |  | Pending
Get the list of Self Service Users from Pavan/Oleg | Get the list of Sefl Service users from upgrade PM poc and provision the users on dev and dev2 and dev3 environments. |  | Fail | Get the SS users list
Get the list of Content editors for the portal from Pavan/Oleg | Get the list of content editors and add them to Dev3 environment |  | Fail | Get the SS users list