## Functional_check-list
	Requirement or User Story Description	Section	Date Executed	Criticality/ Severity / (H, M, L)	Test Case Description	Expected result	Actual Result	Support Feedback	Status	Notes / Ticket URL - as appropriate
1	Configuration check			H
		Platform Version		H	Platform version check: Proceed to the site and click f12 and serch for the "hcp-version"	Platform version should be latest stable platform version as per https://digitalpfizer.atlassian.net/wiki/display/MHPE/HCP+Portal+-+Release+History		Platform version -2.7.5 has issues , please tak it to 2.7.9	Fail
		Features		H	Features (admin/structure/features)	Features that should be enabled: / In HCP Portal Advanced - all should be enabled except - Pfizer HCP2 Example Config, Pfizer HCP2 Example Content, HCP2: Web Standards / In Pfizer - all / In Pfizer Base Features - all / In Pfizer HCP - all / In Pfizer Web Standards - Pfizer Web Standards and Pfizer Web Standards EDetail		HCP Advanced Portal following are disabled: / 1. HCP: Add-this integration / 2. HCP: Multiple Brand URLs / 3. HCP: Deep Linking / 4. HCP: ePermissions / 5. Pfizer HCP2 Marketing / 6. Pfizer HCP2 Material ordering / Pfizer Web Standards following are disabled: / Pfizer Web Standards Edetail	Fail
		Kulu Valley		H	Webinars - Kulu Valley player configuration / /admin/config/media/kuluvalley and local.settings.php	KuluValley settings should be correctly entered for Dev, Stage and Prod		Kuluvalley details are not provided in dev5 case	Fail
		Omniture		H	Omniture settings - modules	3 must be enabled: / -SiteCatalyst / -Pfizer Web Standards / -Pfizer Web Standards HCP2. / - Based on the portal version, webstandards 26 or 27 should be enabled.		Web standards 2.6 and 2.7 are disabled in dev5 env	Fail
				H	Omniture settings - SiteCatalist settings (admin/config/system/sitecatalyst)	SiteCatalist settings should be filled properly. / https://s3.amazonaws.com/pfe_im/js/dev/s_code.js / http://pfizer.112.2o7.net/b/ss/pfizerglobalimdevelopment/1/JS-1.2.2--NS/0 / JS-1.2.2 / User roles tracking: admin, anonymous, authenticated user			Pass
				H	Omniture settings - WebStandart settings (admin/config/system/webstandards)	WebStandard settings should be filled properly / For dev and stage sites should be set up correct market specific and global suites id / For production suites should be different and properly set up: market specific+global / See the details for each market here https://blinkreaction.atlassian.net/wiki/display/PMCG14/HCP+Omniture+Integration		Ask
		Mail Server		H	Mail server check - Email /admin/config/system/smtp	Mail settings should be filled properly.		DONE
					SMTP Hostname	smtp.mailgun.org
					Login	postmaster@pfizerpro.mailgun.org
					Pass	1zznevbtv1n4
					SMTP Port	587
					Use encrypted protocol	Use TLS
					Email from	see email set for Australia on stage
					Email from name	see email from name set for Australia on stage		Ask
		Deploy Configuration							Pass
		Deploy Works						Ask
		Autologout							Pass
		Newscred				Check for the following configuration in local.settings.php with some values: / $conf['pfizer_hcp2_newscred_access_key'] and / $conf['pfizer_hcp2_newscred_collection'] / Also verify the same at /admin/config/hcp/newscred		$conf['pfizer_hcp2_newscred_access_key'] and / $conf['pfizer_hcp2_newscred_collection'] dedtails not providded in local.settings.php	Fail
						Check $conf['pfizer_hcp2_newscred_disable_import'] in local.setting,php. / It should be FALSE for dev3, everything else TRUE including PROD		$conf['pfizer_hcp2_newscred_disable_import'] is given TRUE in global and not in dev cases. For dev3 it is fine	Fail
		Env Variables			$_SERVER should be $_ENV settings	Check $_ENV settings in local.settings.php			Pass
		Brightcove
		Memory Limit			Memory limit 512 all environments	Check whether memory_limit is set to 512 in local.settings.php			Pass
		Error Level			Error level set to 0	Check whether error_level is set to 0 in local.settings.php			Pass
					Secure pages configured	Check secure pages configuartion settings in local.settings.php			Pass
		Error Logs			visit <site_name>/admin/reports/status and check for error logs			Following issues were found: / 1. Composer Manager - Dependencies not installed / 2. Flag - Translation helpers module not found. / 3. HCP: Unexpected content types - Rogue content types were found.	Fail
					Check the browser console for any possible errors and report the same				Pass
		Janrain Configuration

2	Home Page
					Home page design - For Ex. multi-tiled banner - Portugal/Denmark example / (Refer the Epic to check the exact requirement for that market)	Check the banner type as per the Epic ticket			Pass
					Cookie widget in place- Only for EU markets / (Only if mentioned in Epic ticket)	Should be present in bottom left corner (configured in blocks). Check if the Click here link in the pop up is linking to the cookies page.		Not being displayed	Fail
		Footer			Footer menu and pages	Check the footer menus and all the links			Pass

2	Separate bucket Policy
					Check if the separate bucket policy is impelmented in local.settings.php and also test it with sample CSS and JS			Pending
					Check if the separate bucket policy is configured for brand JSON.	Check separate bucket policy implementation for brand json by refresing the xref from admin panel to check of the brand json files are being fetched from right Amazon bucket		Defined globally	Ask

3	Paywall
		Public			Create a public node and check whether the Public specific content gets displayed for anonymous users. Also verify the layout				Pass
		Paywall			Create a paywall node and check whether the Paywall specific content gets displayed or not while in logged out state. Also verify the layout i.e apart from the paywall content the login and registration block should appear.				Pass
		Private			Create a Private node and check whether the Login page is triggered or not while in logged out state. Also verify the layout i.e. login and registration block should appear.				Pass

2	Five star rating	Five Star Rating			Five Star Rating (Widget and fine grain controls) / (Applicable only if Epic has mention of this feature)	Check if 5 star rating is enabled for required content types at /admin/config/hcp/ratings		Not present	Fail

2	GRV
				H	GRV Login, Page after Login	Login should work correctly			Pass
				H	Check translation for GRV log in screen and page after log in	Should be translated properly			Pass
				H	GRV Register, Page after registration	Registration should work correctly. Your account statuse should be "Pending validation". / You can should be not able to log in till your account will be velidated.Registration should work correctly. Your account statuse should be "Pending validation". / You can should be not able to log in till your account will be velidated.Registration should work correctly. Your account statuse should be "Pending validation". / You can should be not able to log in till your account will be velidated.Registration should work correctly. Your account statuse should be "Pending validation". / You can should be not able to log in till your account will be velidated.			Pass
				H	Check translation for GRV registration screen and welcome popup	Should be translated properly			Pass
				H	Check Forgot your password GRV screen	Should work as expected, you should able to change your password			Pass
				H	Check translation for Forgot your password screen and thank you popup	Should be translated properly			Pass
3	Verify Translations for the following sections, pages
				H	Translated site Logo, Main Menu, Sign in/Register	Should be translated			Pass
				H	Mobile menu	Should be translated and contain links: / Pfizer Home, Pfizer Products, Medical Conditions, Support and Services, Contact UsShould be translated and contain links: / Pfizer Home, Pfizer Products, Medical Conditions, Support and Services, Contact UsShould be translated and contain links: / Pfizer Home, Pfizer Products, Medical Conditions, Support and Services, Contact UsShould be translated and contain links: / Pfizer Home, Pfizer Products, Medical Conditions, Support and Services, Contact Us
				H	Footer Menu	Should be translated and match dbtext file on Translation package ticket			Pass
				H	Privacy Policy, Terms of Use	Should be translated and match dbtext file on Translation package ticket			Pass
				H	Translate of titles' banners on Home page	Should be translated			Pass
				H	404 Page	Should be translated			Pass
				H	Contact Us	Should be translated			Pass
				H	Support and Services	Should be translated		Ask
				H	News Archive	Should be translated		Ask
4	Dual language functionality check
				H	Search for dual language site	Search should return content only on the selected language			Pass
				H	Register, Reminder, Ask questions emails for the webinars	Emails should be on the same language as webinars		Register mail checked rest pending
				H	Language selector	Content types should have drop down with language selector - English CA and French CA (no only for HCP Pre-event Survey)		Ask
				H	Webinar Branding	Only brand with the same language as webinar has should be selectable
5	Search field functionality
				H	Check translation for search field near the main menu, placeholder	Should be translated properly			Pass
				H	User access for search field	Available to ANON and AuthN users		Not available for anonymous users	Fail
				H	Perform search using search field near the main menu, try empty key word, one word, key words that have two words, words that have special symbols	Confirm that: / 1. Search should work with empty key word. / 2. Search should work with one word / 3. Search should work with key words that have two words. / 4. Search should work with key words that have special symbols.Confirm that: / 1. Search should work with empty key word. / 2. Search should work with one word / 3. Search should work with key words that have two words. / 4. Search should work with key words that have special symbols.Confirm that: / 1. Search should work with empty key word. / 2. Search should work with one word / 3. Search should work with key words that have two words. / 4. Search should work with key words that have special symbols.			Pass
				H	Observe search results page, check translation	Search page should provide correct serch results and displayed properly. Should have "Search" header on the banner. Should be translated properly			Pass
				H	Perform search using search field on search results page	Search field on search page should work the same way as search field on the header			Pass
6	Product page
				H	Proceed to the product page, check translations	You should be able to proceed only as authorized user, page should be properly translated			Pass
				H	Jump to for Products on a Product page	You should be able to jump to the correct block of the products by clicking a letter of the alphabet			Pass
				H	Verify popup for external links, check translation	If link leades to the different domain so you should be able to see popup and after link should be opened in new tab. / Popup should be properly translatedIf link leades to the different domain so you should be able to see popup and after link should be opened in new tab. / Popup should be properly translatedIf link leades to the different domain so you should be able to see popup and after link should be opened in new tab. / Popup should be properly translated		Pop up displayed in english	Fail
				H	Check the product links	All links should have correct page opened. / All internal links should lead to the same test/stage domain (dev5 should not point to dev3 for example)All links should have correct page opened. / All internal links should lead to the same test/stage domain (dev5 should not point to dev3 for example)			Pass
				H	Check microsites, check translation on microsites	All links should have correct page opened. / Pages should opened without issues. Microsites should be translated.All links should have correct page opened. / Pages should opened without issues. Microsites should be translated.			Pass
7	Medical Conditions
				H	Go to – medical condition landing page, check translation	Page should be properly translated		Where to find this link
8	Material Ordering							Not present
				H	Go to "Material Ordering" page and observe the page, check translation	Should be visible for authorized user, page should be properly translated
				H	Check dropdown for quantity of products	Should be able to change quantity of products
				H	Check filters	Should be able to use filter
				H	Check download buttons	Should be able to download attached documents
				H	Check Patient materials and HCP materials tabs	Should be able to navigate between Patient materials and HCP materials.
				H	Create application or material /admin/content/hcp-material-ordering	Confirm products are in the correct category - patient or HCP materials.
				H	Try to add some items to the basket, check translation in the basket	Should be able to add to the basket and see pop up confirmation message. Basket with items is shown in right hand of page prior to completing order.
				H	Try to remove items from the basket	Should be able to remove items from basket
				H	Try to order some items: proceed to the order form, fill all fields with correct data (use real test email) and submit the form. Check translation on the order form page.	Should be able to complete order and confirm can enter information into correct fields. Should be translated properly
				H	Observe the page after submittiong, check translaion on thank you page	Shoud be able to see order confirmation message after completing order. Translation should be correct.
				H	Check confirmation email received to the test email. Check translation in this email.	User should receive email after submitting their order. Email should be translated properly
				H	Proceed to the order form page and check fields validation and error messages (translation)	All fields should work properly and error messages should be translated.
9	Stock availability
				H	Go to Stock availability main menu section. Observe the page, check translation	Stock availability main menu section should be availble. / You should able to see the list of products. / Page should be properly translated.
				H	Check the filters: ABCD, drop-down and search field	Filters shouls work as expected, the list should correctly reflect to the filter
10	Clinical information/QuickList
				H	QuickList - confirm items can be reordered using quicklist / http://prntscr.com/93ug0w / http://prntscr.com/93ug9z	As Admin, select Content link and filter by HCP Indication page, Edit a Product and reorder clinical information using drag and drop interface or change their respective weights. / Save and validate clinical information reflects the changes made.			Pass
11	User roles/permissions
				H	HCP User Roles check & permissions:	Site should have roles below: / anonymous / site_admin (roles: ALL) / content_admin (roles: Content Admin, Presentation Editor, Webinar Content Editor) / content_editor (roles: Content Editor, Presentation Editor, Webinar Content Editor) / common_user (role: Authenticated User)		Result not clear
				H	Anonymous / Try to proceed to any section in main menu / Try to proceed to any sub-page not visible section or product page	Home page should be displayed / Should not have access to the folloving sections: / Products page and product microsites / Can see Medical resources page but can not proceed to sub-pages / Can see Support page but can not proceed to sub-pages		Could not find medical resources page. Rest are working fine
12	On-demand Event
				H	Create Webinar - On-demand Event Videos	You should be able to create on demand webinar and webinar listings appear on correct listing pages - Support and Services.		Created webinar, but still need clarification over the listing page
				H	Observe created page with webinar, check translation for all non custom items	All non custom items should be properly translated
				H	Edit Webinar and change vebinar statuses	Confirm can create live webinar as Paywall and Private types - should prompt Anonymous users to login.			Pass
				H	Webinars player check / Create Live event, specify real Kuluvalley Alias, set webinar status to live to see player	Webinar player should work and can be played in full screen mode and small player. / Confirm webinar player works on mobile and tablet as well as desktop.		Ask
				H	Play the video in full screen mode.	Video should be played in full screen mode.		Ask
				H	Add five star rating, set your raiting, check translations in status messages	You should be able to see raiting block		Not present	Fail
				H	Paywall pages - confirm creation and access	Login as admin in Pfizer site and create a On-demand Event page with status set as Paywalled / Browse to page as Anonymous user - should see login page and paywall teaser message. / Browse to page as Authenticated user - should see On-demand Event.			Pass
				H	Private pages - confirm creation and access	"Login as admin in Pfizer site and create an On-demand Event with status set as Private / Browse to page as Anonymous user - should see login page / Browse to page as Authenticated user - should see private On-demand Event page."			Pass
				H	Public pages	Anonymous and Authenticated users can access.			Pass
13	Live Streamed Events
				H	Create Webinar - Live Streamed Events / (HCP: Live Webinar) / Put time 3h+15min forvard	You should be able to create on live webinar and should appear on correct listing pages. / Confirm can create live webinar as Paywall and Private types - should prompt Anonymous users to login. / Select all check-boxes in "Manage email reminder preferences" popup and click"Save and close"		Manage email pending. Rest are working fine.
				H	Observe created page with webinar, check translation, pay attention to all non custom items you see during the testing (translation in popups, messages, email notifications)	All non custom items should be properly translated			Pass
				H	Register for Live Streamed Events / Verify Registration email	Confirm user can register for webinar and receives confirmation email - and all links (including footer) are as expected. / Confirm user can use the 'Add to Calendar' feature to add an event to their calendar. / Verify the calendar appointment contains the following text: / Subject: Title of the program / Thank you for registering for the XXX event. / To view this event please click here link / We would suggest you visit the link five minutes before start time to allow time to connect. / This is a system generated calendar invite…. / To report on Adverse event…. / ISI copy and Links (if branded)… / Verify calendar invite should be attached in the email.		Check
				H	Run cron and verify reminder email / If cron is not properly configured and you can use the following admin section to receive an example of reminder email - /admin/config/hcp/webinar_mlr / In Webinar select just created Online webinar. In email address type your real email, wherever reminder and registration messages will be sent to. Fill in "Username" field and press "Send" button.	You should be able to receive reminder email. / Check the link for webinar - it should lead derectly to the current webinar. / The rest links inside should lead to the current domain. / Some images can be not loaded - it is ok for dev environment. / If you will download email, confirm https and open it in browser - all images will be displayed properly		Ask
				H	Create webinars for 1day in future and for 1 week forvard the same way as is was for 3h webinar. / Register to this webinar and run cron	Confirm user can register for webinar and receives registration email		Ask
				H	Check reminder emails for 1day and 1week before event	You should be able to receive reminder email. / Check the link for webinar - it should lead derectly to the current webinar. / The rest links inside should lead to the current domain. / Some images can be not loaded - it is ok for dev environment. / If you will download email, confirm https and open it in browser - all images will be displayed properlyYou should be able to receive reminder email. / Check the link for webinar - it should lead derectly to the current webinar. / The rest links inside should lead to the current domain. / Some images can be not loaded - it is ok for dev environment. / If you will download email, confirm https and open it in browser - all images will be displayed properlyYou should be able to receive reminder email. / Check the link for webinar - it should lead derectly to the current webinar. / The rest links inside should lead to the current domain. / Some images can be not loaded - it is ok for dev environment. / If you will download email, confirm https and open it in browser - all images will be displayed properlyYou should be able to receive reminder email. / Check the link for webinar - it should lead derectly to the current webinar. / The rest links inside should lead to the current domain. / Some images can be not loaded - it is ok for dev environment. / If you will download email, confirm https and open it in browser - all images will be displayed properly		Ask
				H	Set your real email during webinar creation / Open "Ask a question" popup and send your question / Check email receivedSet your real email during webinar creation / Open "Ask a question" popup and send your question / Check email receivedSet your real email during webinar creation / Open "Ask a question" popup and send your question / Check email receivedSet your real email during webinar creation / Open "Ask a question" popup and send your question / Check email received	You should be able to receive "Ask a question to the speaker" email / Link with webinar title should lead to the current webinar / Email should look and styled properly - http://prntscr.com/94x0m3You should be able to receive "Ask a question to the speaker" email / Link with webinar title should lead to the current webinar / Email should look and styled properly - http://prntscr.com/94x0m3You should be able to receive "Ask a question to the speaker" email / Link with webinar title should lead to the current webinar / Email should look and styled properly - http://prntscr.com/94x0m3You should be able to receive "Ask a question to the speaker" email / Link with webinar title should lead to the current webinar / Email should look and styled properly - http://prntscr.com/94x0m3		Ask
				H	Five Star Rating check	You should be able do enable or disable raiting block for Live streaming events. / User should be able to choose raiting level. / Rating should display correct rating on all sections where Live streaming event is displayed (listing pages and detailed page) / Anonymous users should not see avetage rating.You should be able do enable or disable raiting block for Live streaming events. / User should be able to choose raiting level. / Rating should display correct rating on all sections where Live streaming event is displayed (listing pages and detailed page) / Anonymous users should not see avetage rating.You should be able do enable or disable raiting block for Live streaming events. / User should be able to choose raiting level. / Rating should display correct rating on all sections where Live streaming event is displayed (listing pages and detailed page) / Anonymous users should not see avetage rating.You should be able do enable or disable raiting block for Live streaming events. / User should be able to choose raiting level. / Rating should display correct rating on all sections where Live streaming event is displayed (listing pages and detailed page) / Anonymous users should not see avetage rating.		Not present	Fail
				H	Webinar Registration Report	As Admin user, navigate to Report section and Report landing page will load. / Click on 'Webinar Registration Report' and confirm see: / Filters: Event date and title / Fields: email address-first name-last name-Registration date-Webinar title-Attended Webinar-Completed Webinar. / Report can be filtered and sorted by Event name and date. / Report can be exported in excel format.As Admin user, navigate to Report section and Report landing page will load. / Click on 'Webinar Registration Report' and confirm see: / Filters: Event date and title / Fields: email address-first name-last name-Registration date-Webinar title-Attended Webinar-Completed Webinar. / Report can be filtered and sorted by Event name and date. / Report can be exported in excel format.As Admin user, navigate to Report section and Report landing page will load. / Click on 'Webinar Registration Report' and confirm see: / Filters: Event date and title / Fields: email address-first name-last name-Registration date-Webinar title-Attended Webinar-Completed Webinar. / Report can be filtered and sorted by Event name and date. / Report can be exported in excel format.As Admin user, navigate to Report section and Report landing page will load. / Click on 'Webinar Registration Report' and confirm see: / Filters: Event date and title / Fields: email address-first name-last name-Registration date-Webinar title-Attended Webinar-Completed Webinar. / Report can be filtered and sorted by Event name and date. / Report can be exported in excel format.
				H	Paywall pages - confirm creation and access	Login as admin in Pfizer site and create a Live Streamed Event page with status set as Paywalled / Browse to page as Anonymous user - should see login page and paywall teaser message. / Browse to page as Authenticated user - should see Live Streamed Event.Login as admin in Pfizer site and create a Live Streamed Event page with status set as Paywalled / Browse to page as Anonymous user - should see login page and paywall teaser message. / Browse to page as Authenticated user - should see Live Streamed Event.Login as admin in Pfizer site and create a Live Streamed Event page with status set as Paywalled / Browse to page as Anonymous user - should see login page and paywall teaser message. / Browse to page as Authenticated user - should see Live Streamed Event.Login as admin in Pfizer site and create a Live Streamed Event page with status set as Paywalled / Browse to page as Anonymous user - should see login page and paywall teaser message. / Browse to page as Authenticated user - should see Live Streamed Event.		Could not check streamed events
				H	Private pages - confirm creation and access	"Login as admin in Pfizer site and create an Live Streamed Event with status set as Private / Browse to page as Anonymous user - should see login page / Browse to page as Authenticated user - should see private Live Streamed Event page.""Login as admin in Pfizer site and create an Live Streamed Event with status set as Private / Browse to page as Anonymous user - should see login page / Browse to page as Authenticated user - should see private Live Streamed Event page.""Login as admin in Pfizer site and create an Live Streamed Event with status set as Private / Browse to page as Anonymous user - should see login page / Browse to page as Authenticated user - should see private Live Streamed Event page.""Login as admin in Pfizer site and create an Live Streamed Event with status set as Private / Browse to page as Anonymous user - should see login page / Browse to page as Authenticated user - should see private Live Streamed Event page."		Could not check streamed events
				H	Public pages	Anonymous and Authenticated users can access.
14	eDetail Presentation - Digital Presentation
				H	Create eDetail Presentation - Digital Presentation / Create Digital Presentation, choose 99348 in "Pfizer Pitcher" field, fill the rest required fields and publish. / Check bility to select eDetail from listCreate eDetail Presentation - Digital Presentation / Create Digital Presentation, choose 99348 in "Pfizer Pitcher" field, fill the rest required fields and publish. / Check bility to select eDetail from listCreate eDetail Presentation - Digital Presentation / Create Digital Presentation, choose 99348 in "Pfizer Pitcher" field, fill the rest required fields and publish. / Check bility to select eDetail from listCreate eDetail Presentation - Digital Presentation / Create Digital Presentation, choose 99348 in "Pfizer Pitcher" field, fill the rest required fields and publish. / Check bility to select eDetail from list	You should be able to create edetail presentation. / Presentation should be displayed in "Support & Services" for some product http://prntscr.com/8sxqro or on /support page depends on the settings here http://prntscr.com/8sxr1g / Number of eDetails displayed in brackets / Check also "Support & Services" block on Home pageYou should be able to create edetail presentation. / Presentation should be displayed in "Support & Services" for some product http://prntscr.com/8sxqro or on /support page depends on the settings here http://prntscr.com/8sxr1g / Number of eDetails displayed in brackets / Check also "Support & Services" block on Home pageYou should be able to create edetail presentation. / Presentation should be displayed in "Support & Services" for some product http://prntscr.com/8sxqro or on /support page depends on the settings here http://prntscr.com/8sxr1g / Number of eDetails displayed in brackets / Check also "Support & Services" block on Home pageYou should be able to create edetail presentation. / Presentation should be displayed in "Support & Services" for some product http://prntscr.com/8sxqro or on /support page depends on the settings here http://prntscr.com/8sxr1g / Number of eDetails displayed in brackets / Check also "Support & Services" block on Home page		Ask
				H	Observe created page with presentation, check translation, pay attention to all non custom items you see during the testing (translation in popups, messages)	All non custom items should be properly translated		Ask
				H	eDetail player check	eDetail player should work		Ask
				H	Five Star Rating check	You should be able do enable or disable raiting block for eDetail Presentation. / User should be able to choose raiting level. / Rating should display correct rating on all sections where eDetail Presentation is displayed (listing pages and detailed page) / Anonymous users should not see avetage rating.You should be able do enable or disable raiting block for eDetail Presentation. / User should be able to choose raiting level. / Rating should display correct rating on all sections where eDetail Presentation is displayed (listing pages and detailed page) / Anonymous users should not see avetage rating.You should be able do enable or disable raiting block for eDetail Presentation. / User should be able to choose raiting level. / Rating should display correct rating on all sections where eDetail Presentation is displayed (listing pages and detailed page) / Anonymous users should not see avetage rating.You should be able do enable or disable raiting block for eDetail Presentation. / User should be able to choose raiting level. / Rating should display correct rating on all sections where eDetail Presentation is displayed (listing pages and detailed page) / Anonymous users should not see avetage rating.		Not present	Fail
				H	Paywall pages - confirm creation and access	Login as admin in Pfizer site and create a eDetail page with status set as Paywalled / Browse to page as Anonymous user - should see login page and paywall teaser message. / Browse to page as Authenticated user - should see content page.Login as admin in Pfizer site and create a eDetail page with status set as Paywalled / Browse to page as Anonymous user - should see login page and paywall teaser message. / Browse to page as Authenticated user - should see content page.Login as admin in Pfizer site and create a eDetail page with status set as Paywalled / Browse to page as Anonymous user - should see login page and paywall teaser message. / Browse to page as Authenticated user - should see content page.Login as admin in Pfizer site and create a eDetail page with status set as Paywalled / Browse to page as Anonymous user - should see login page and paywall teaser message. / Browse to page as Authenticated user - should see content page.			Pass
				H	Private pages - confirm creation and access	"Login as admin in Pfizer site and create a eDetail page with status set as Private / Browse to page as Anonymous user - should see login page / Browse to page as Authenticated user - should see content page.""Login as admin in Pfizer site and create a eDetail page with status set as Private / Browse to page as Anonymous user - should see login page / Browse to page as Authenticated user - should see content page.""Login as admin in Pfizer site and create a eDetail page with status set as Private / Browse to page as Anonymous user - should see login page / Browse to page as Authenticated user - should see content page.""Login as admin in Pfizer site and create a eDetail page with status set as Private / Browse to page as Anonymous user - should see login page / Browse to page as Authenticated user - should see content page."
				H	Public pages	Anonymous and Authenticated users can access.
15	NewsCred Articles
				H	Create NewsCred Articles	Content editor should be able to create news articles
				H	Observe created page with article, check translation, pay attention to all non custom items you see during the testing (translation in popups, messages)	All non custom items should be properly translated			Pass
				H	Check that NewsCred Articles is displayed at the correct places (in news list, as one news, on home page if was promoted)	NewsCred Articles should be displayed. / Confirm only Articles published within ${period} are displayed on News ArticlesNewsCred Articles should be displayed. / Confirm only Articles published within ${period} are displayed on News ArticlesNewsCred Articles should be displayed. / Confirm only Articles published within ${period} are displayed on News Articles			Pass
				H	Check that NewsCred is displayed	NewsCred should be displayed on home page and News pages. / Verify whether the following fields are enabled and editable respectively: / Title / Language / Page Type / Content Type / Content Build No / Article Abstract / Article By-line / Article Preview Picture / Article Body / Article Picture / Specialities / ProfessionsNewsCred should be displayed on home page and News pages. / Verify whether the following fields are enabled and editable respectively: / Title / Language / Page Type / Content Type / Content Build No / Article Abstract / Article By-line / Article Preview Picture / Article Body / Article Picture / Specialities / ProfessionsNewsCred should be displayed on home page and News pages. / Verify whether the following fields are enabled and editable respectively: / Title / Language / Page Type / Content Type / Content Build No / Article Abstract / Article By-line / Article Preview Picture / Article Body / Article Picture / Specialities / Professions			Pass
				H	Check that the last added news is displayed and is at the first place of NewsCred	The last new article should be displayed properly. / When Anonymous user tries to click on a Newscred item, they are redirected to login page. / When Authenticated user tries to click on a Newscred item, they are redirected to the appropriate news article page.The last new article should be displayed properly. / When Anonymous user tries to click on a Newscred item, they are redirected to login page. / When Authenticated user tries to click on a Newscred item, they are redirected to the appropriate news article page.The last new article should be displayed properly. / When Anonymous user tries to click on a Newscred item, they are redirected to login page. / When Authenticated user tries to click on a Newscred item, they are redirected to the appropriate news article page.
				H	Five Star Rating check	Rating should be present on selected content (user can choose), rating should display correct rating / No 'my rating widget' is displayed on any listing page. / Anonymous users should not see avetage rating. / Five star widget is listed on (as available) Product microsite pages, Medical condition pages within microsites, Support and Services content pages, Webinar content pages, eDetail content pages and News content pages.Rating should be present on selected content (user can choose), rating should display correct rating / No 'my rating widget' is displayed on any listing page. / Anonymous users should not see avetage rating. / Five star widget is listed on (as available) Product microsite pages, Medical condition pages within microsites, Support and Services content pages, Webinar content pages, eDetail content pages and News content pages.Rating should be present on selected content (user can choose), rating should display correct rating / No 'my rating widget' is displayed on any listing page. / Anonymous users should not see avetage rating. / Five star widget is listed on (as available) Product microsite pages, Medical condition pages within microsites, Support and Services content pages, Webinar content pages, eDetail content pages and News content pages.		Ask
				H	Paywall pages - confirm creation and access	Login as admin in Pfizer site and create a Article page with status set as Paywalled / Browse to page as Anonymous user - should see login page and paywall teaser message. / Browse to page as Authenticated user - should see articlee.Login as admin in Pfizer site and create a Article page with status set as Paywalled / Browse to page as Anonymous user - should see login page and paywall teaser message. / Browse to page as Authenticated user - should see articlee.Login as admin in Pfizer site and create a Article page with status set as Paywalled / Browse to page as Anonymous user - should see login page and paywall teaser message. / Browse to page as Authenticated user - should see articlee.			Pass
				H	Private pages - confirm creation and access	"Login as admin in Pfizer site and create an Article with status set as Private / Browse to page as Anonymous user - should see login page / Browse to page as Authenticated user - should see private Article page.""Login as admin in Pfizer site and create an Article with status set as Private / Browse to page as Anonymous user - should see login page / Browse to page as Authenticated user - should see private Article page.""Login as admin in Pfizer site and create an Article with status set as Private / Browse to page as Anonymous user - should see login page / Browse to page as Authenticated user - should see private Article page."			Pass
				H	Public pages	Anonymous and Authenticated users can access.			Pass
16	Quick Poll
				H	Login as a admin or content editor Create a content using "HCP Poll: Quick Poll" content type.	Quick Poll should work . / Quick Polls can be created by admin user and includes: radio buttons, checkboxes, select lists, free text boxes. / Can embed quick polls into: Portal home page, Microsite landing pages, Microsite content pages, News Article pages, Support and Services content pages, Webinar pages, eDetail pages. / Confirm Authenticated user can submit quick poll. / Quick poll response will display aggregate data, rather than a thank you message.Quick Poll should work . / Quick Polls can be created by admin user and includes: radio buttons, checkboxes, select lists, free text boxes. / Can embed quick polls into: Portal home page, Microsite landing pages, Microsite content pages, News Article pages, Support and Services content pages, Webinar pages, eDetail pages. / Confirm Authenticated user can submit quick poll. / Quick poll response will display aggregate data, rather than a thank you message.Quick Poll should work . / Quick Polls can be created by admin user and includes: radio buttons, checkboxes, select lists, free text boxes. / Can embed quick polls into: Portal home page, Microsite landing pages, Microsite content pages, News Article pages, Support and Services content pages, Webinar pages, eDetail pages. / Confirm Authenticated user can submit quick poll. / Quick poll response will display aggregate data, rather than a thank you message.
				H	Observe created page with quick poll, check translation, pay attention to all non custom items you see during the testing (translation in popups, messages)	All non custom items should be properly translated
17	Customer feedback
				H	Login as a admin or content editor Create a content using "HCP Poll: Customer Feedback" content type.	Polling: Customer feedback should work / Admin user should be able to create Customer Feedback Polls. / Verify additional field can be added to display on front end or hidden by admin (detailed feedback field). / Admin can define a question type that appears on the front end. / Theming matches the rest of HCP Portal / Customer Feedback polls and be embedded into: Portal home page, Microsite landing page, News Article pages, Support and Services content pages, Webinar pages, eDetail pages, internal listing/landing pages. / Anonymous user should see: Feedback poll block asking user to login to vote. / Authenticated user can see poll as expected. / Authenticated user can complete and submit poll and see Thank you message.Polling: Customer feedback should work / Admin user should be able to create Customer Feedback Polls. / Verify additional field can be added to display on front end or hidden by admin (detailed feedback field). / Admin can define a question type that appears on the front end. / Theming matches the rest of HCP Portal / Customer Feedback polls and be embedded into: Portal home page, Microsite landing page, News Article pages, Support and Services content pages, Webinar pages, eDetail pages, internal listing/landing pages. / Anonymous user should see: Feedback poll block asking user to login to vote. / Authenticated user can see poll as expected. / Authenticated user can complete and submit poll and see Thank you message.Polling: Customer feedback should work / Admin user should be able to create Customer Feedback Polls. / Verify additional field can be added to display on front end or hidden by admin (detailed feedback field). / Admin can define a question type that appears on the front end. / Theming matches the rest of HCP Portal / Customer Feedback polls and be embedded into: Portal home page, Microsite landing page, News Article pages, Support and Services content pages, Webinar pages, eDetail pages, internal listing/landing pages. / Anonymous user should see: Feedback poll block asking user to login to vote. / Authenticated user can see poll as expected. / Authenticated user can complete and submit poll and see Thank you message.
				H	You would see in the created content the options are listed	Customer wants this to be displayed in the following order by default: / Yes / No / MaybeCustomer wants this to be displayed in the following order by default: / Yes / No / MaybeCustomer wants this to be displayed in the following order by default: / Yes / No / Maybe
				H	Observe customer feedback block, check translation, pay attention to all non custom items you see during the testing (translation in popups, messages)	All non custom items should be properly translated
18	Velaro Chat - NOT APPLICABLE
				H	Test Velaro Chat Interface – check that the chat window appears	The Velaro Chat link will pass the username and email address of the current user to the Support Member at Velaro. These values are passed as query elements within the URL which the Velaro system will pick up.
				H	Observe chat block, check translation, pay attention to all non custom items you see during the testing (translation in popups, buttons, messages)	All non custom items should be properly translated
				H	Test Specialty and Profession – Log in as two GRV users with different professions or specialties	Check that their chat URLs are returning different values. Alternately, edit the same user (log out and log back in to make sure it takes effect) so they have a different Specialty and then open the chat window again.
19	Pfizer Contact widget
				H	Go as admin user on home page and click "Customize page", choose free area and find "Contact widget"	Admin user should be able to create Pfizer Contact widget
				H	Observe contact widget, check translation, pay attention to all non custom items you see during the testing (translation in popups, buttons, messages)	All non custom items should be properly translated
				H	Configure widget, save and check the widjet on page	Widjet should be broperly displayed
				H	Click edit contact and fill all available fields, save it and check on page	You should be able to edit widget and save it. All entered data should be properly displayed			Pass
20	GUI testing			H
	Testing in all supported browsers:			H	Font accuracy check	Font family implemented as per design. All fonts are consistent.			Pass
	FF (most recent Win)			H	Favicon	The favicon should be visible.			Pass
	GC (most recent Win)			H	Main menu layout, search field	Should be available and displayed properly for all supported browsers on DT and Mobile			Pass
	Safari (most recent MacOS)			H	Home page: DLs, Views (news, articles ets)	DLs should be centered, you should be able to switch DL using buttons / New Home page check: / Depends on market - should have slider or multi-tiled banner OR use the standard home page available in v2.1-2.3. / Home page should show News link and News quick list block.DLs should be centered, you should be able to switch DL using buttons / New Home page check: / Depends on market - should have slider or multi-tiled banner OR use the standard home page available in v2.1-2.3. / Home page should show News link and News quick list block.		Ask
	IE9-11 (Win)			H	Footer alignment, "Back to top" anchor link	Footer should be displayed without issues			Pass
	iPhone 6 (most recent iOS)			H	Product page	Product page should be displayed properly			Pass
	iPad (most recent)			H	Medical conditions	Medical Conditions page should be displayed properly
	Android mobile (most recent)			H	Support and services	Support and Services page should be displayed properly			Pass
	Note: use general browsers during the fuctional testing: FF, GC. / For GUI testing check only the rest browser mentioned in this list - it will save time			H	GRV "log in" popup view	Popup should be properly displayed in all supported browsers on DT and Mobile, text in fields should be properly displayed. Placeholders should begin from the capital letter. Popup should be visible and you should not have to scroll up to see it on mobile.			Pass
				H	GRV "Registration" popup view	Popup should be properly displayed without issues. Placeholders should begin from the capital letter. Popup should be visible and you should not have to scroll up to see it. All fields should be edatable. Drop-downs should work as expected.			Pass
				H	GRV "Forgot your password" popup	Popup should be properly displayed in all supported browsers on DT and Mobile, text in fields should be properly displayed. Placeholders should begin from the capital letter. Popup should be visible and you should not have to scroll up to see it on mobile.			Pass
				H	Banner Image Responsiveness	Open site on wide viewport and view a page with standard banner 1 image. / confirm wide viewport banner size is: Size of banner 1 is 1365 x 240 / Desktop Viewport banner size is: Size of banner 1 is 960 x 240 / Large tablet viewport banner size is Size of banner 1 is 640 x 180 / Small table viewport banner size is: Size of banner 1 is 480 x 130 / Mobile viewport banner size is: Size of banner 1 is 340 x 105			Pass
				H	Check created during the testing content, use long headers and description text, check layout	Newly created content should be displayed without any issues
21	Omnichure testing/Report
				H	Omniture variables check	Variables should be correct and linked to the paths/clicks - see attached required Omniture testing Tab need to verify actions are recorded in the Market-specific site analytics suite. / Reffer to the "Omnichure testing" tab for the details

## Omniture_Testing
		RS Title	HCP Portal Australia Dev	HCP Portal
		URL	pfpfproaudev5.prod.acquia-sites.com
User Exp.	Event / location	Img Req. Type	RSID 1	RSID 2	Issue / Observation (if any)	Test Status (PASS, FAIL, N/A)
Flow	Homepage	onLoad	pfizerhcpaustraliastage	pfizerglobalimdevelopment	No tracking for anonymous user, works fine for logged in user	Passed
Use Case # 1	Registration Initiated	Onclick	pfizerhcpaustraliastage	pfizerglobalimdevelopment	(Event8: Registration Initiated - should be requested) / Action – event8 should be triggered from the request having correct link name.	Passed
Use Case # 2	Registration Completed	Onclick	pfizerhcpaustraliastage	pfizerglobalimdevelopment	Event7 (page view) Is triggered for registration completed. / (Correct event: Event9 – Registration Completed)	Passed
Use Case # 3	Login Initiated	Onclick	pfizerhcpaustraliastage	pfizerglobalimdevelopment	Event36: Login Initiated - should be requested) / Action – event36 should be triggered from the request having correct link name.	Passed
Use Case # 4	Login Complete	Onclick	pfizerhcpaustraliastage	pfizerglobalimdevelopment	Single img request with Event37 (page view) Is triggered for login completed. / (Correct event: Event37 – Login Completed)	Passed
Use Case # 5	File Download	Onclick	pfizerhcpaustraliastage	pfizerglobalimdevelopment	No files to download
Use Case # 6	Exit Link	Onclick	pfizerhcpaustraliastage	pfizerglobalimdevelopment		Passed
Use Case # 7	Video Tracking	Onclick	pfizerhcpaustraliastage	pfizerglobalimdevelopment		Passed
Use Case #8	Customer Feedback Poll - Complete	Onclick	pfizerhcpaustraliastage	pfizerglobalimdevelopment	Check that In Adobe Analytics it must be possible to track the number of users who successfully complete a Customer Feedback Poll. - No events appears	Pass	http://prntscr.com/9op7v4

Instructions
Ensure you have the market-specific Omnniture suite name and access to it on the Omniture Adobe Analytics site analytics suite.
Create a tab for each use case listed above
Enter details on each tab as noted in example on:https://smscvt.atlassian.net/browse/MD-809
Test actions on the website and validate they are logged on the market-specific site analytics suite
Take screenshots of findings
Test needs to be done during development QA AND as part of MTP validation.
Submit completed report (including pass and fail information) to PM or upload to QA ticket.