## Checklist
Deployment Checklist for: Market Name |  | HCP Portal UK |  | Platform | 2.7.3 | Updated: |  | 2016-08-05 | Vasiliy Zaytsev | Target MTP date:
| HCP 2.7 |  |  | Sub Platform Version |  | Production: |  | URL | www.pfizerpro.fr | Stage: | pfpfprofrstg.prod.acquia-sites.com (2.6.8)
[8 empty] | Project Team POC | Project Team | Dev3 | pfpfprofrdev3.prod.acquia-sites.com (2.6.8)
[8 empty] | L3 Team POC | Manish Goyal | Dev5 | pfpfprofrdev5.prod.acquia-sites.com (2.7.7)
[8 empty] | Content Team POC | Content Team | Stg2 - Comparison | pfpfprofrtest2.prod.acquia-sites.com (2.6.8)
[8 empty] | Pfizer BT POC | BT | Latest Code | pfpfprofrdev5.prod.acquia-sites.com (2.7.7)
[8 empty] | Support POC | Diksha Koul | Latest Content | pfpfprofrdev4.prod.acquia-sites.com (2.7.7)
# | Group | Item | Category | Timeframe Prior to MTP (days)? |  | Done? | Support Comments | Owner | Date Complete | Confirmed By | Notes
1 | General | If site is Soft Launced? |  |  |  |  | Please provide input | Diksha Koul
2 | General | If market solft launced, Has MTP package received from Project team? |  |  |  |  | Please provide input | Diksha Koul
3 | General | On which enviroemnt is the latest code residing |  |  |  |  | Please provide input | Manish Goyal
4 | General | On which environment is the latest content residing |  |  |  |  | Please provide input | Content Team
5 | General | Are CPE/STG/PROD having same platform and HCP subplatform? |  |  |  | No |  | Diksha Koul | 2016-09-07 | Vasiliy | It's an upgrade only dev5 is on 2.7
6 | General | Are there any open Zendesk tickets for this portal? |  |  |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy | No zendesk tickets related to this upgrade that our team is aware of
7 | SDLC | Has a Compliance Risk Profile (CRP) & a CMDB record been generated? https://docs.digitalpfizer.com/sdlc-documentation/cmdb-iprm | Security | 30 |  |  | Please provide input | Project Team
8 | SDLC | Has the translation template been completed by the market? |  | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy | Nothing was changed in 2.7 comparing to 2.6
9 | DNS | Verify the domain name is secured and using a standard Pfizer name server. http://www.whois.com or other in-market service | DNS | ASAP |  |  |  | BT
10 | Security | Is SSL certificate configured for primary domain. (Any page that captures user information needs to be on SSL) | SSL | 15 |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
11 | Metrics | Is Omniture Report suite configured? |  | 15 |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy | Test cases and report provided - Page and Features
12 | Acquia | Check that the production environment has 160MB of APC memory set https://www.pfpfproXX.prod.acquia-sites.com/ACQUIA_MONITOR Raise a support ticket if not to get this fixed. |  | 15 |  | N/A | Can you please check this from Global support ? Ideally this information should be shared with HCP support at the time of transition | Diksha Koul | 2016-09-07 | Vasiliy | We don’t have access to this anymore -
13 | Acquia | Confirm with BT Support that system CRON is enabled on production to run every 15 minutes (4 times an hour) |  | 7 |  | N/A | Please provide input | Diksha Koul | 2016-09-07 | Vasiliy | Site is live
14 | Custom | Have any custom code been written by Project Team? Is code reviewed? | - | 7 |  | Yes | What code changes were done, please share the details ? | Diksha Koul | 2016-09-07 | Vasiliy | Coder report provided
15 | Custom | Have any custom code been written by L3 support team? Is code reviewed? | - | 7 |  |  | Please provide input | Manish Goyal
16 | SDLC | Have you reviewed JIRA for open tickets? https://digitalpfizer.atlassian.net/ |  | 7 |  | Yes | Please provide the reason why JIRA tickets are open in EPIC mentioned? | Diksha Koul | 2016-09-07 | Vasiliy | https://digitalpfizer.atlassian.net/browse/PUVTMM-214
17 | Custom | Has Project Team run the Coder Report on custom modules/code and upload these reports to the deployment documents folder? | Deploy | 5 |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy | Also run on contrib and features
18 | Custom | Has L3 Team run the Coder Report on custom modules/code and upload these reports to the deployment documents folder? | Deploy | 5 |  |  | Please provide input | Manish Goyal
19 | Janrain | Have you notified the Janrain team of Production deployment schedule (email at least one week in advance)? | GRV | 7 |  | N/A |  | Diksha Koul | 2016-09-07 | Vasiliy | Site is live
20 | Janrain | Have you confirmed that final, approved GRV screens have been deployed to GRV Production (Amazon)? https://github.com/pfizer/janrain_capture_screens | GRV | 5 |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
21 | Kuluvalley | Is pfizer_kuluvalley enabled? Has the Kulu Valley player configurations for DEV been confirmed and added to local.settings.php? | Kulu Valley | 5 |  | Yes | In the local settings file, there is no separate case for Dev5 environment. Please provide the reason for this. | Diksha Koul | 2016-09-07 | Vasiliy
22 | Kuluvalley | Has the Kulu Valley player configurations for Stage and Production been confirmed and added to local.settings.php? | Kulu Valley | 5 |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
23 | Janrain | Is pfizer_grv enabled? |  | 5 |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
24 | Janrain | Have you requested the Production GRV configuration information and verified the correct settings in the local.settings.php file? |  | 5 |  | Yes | No separate janrain settings for Dev5 . Please provide the reason for this deviation. | Diksha Koul | 2016-09-07 | Vasiliy | Prod GRV was not changed
25 | Pitcher | (2.3) Has Pitcher Client creation been requested from BT-SUPPORT? Has Pitcher been enabled ( pfizer_pitcher ) and configured for site? |  | 5 |  | N/A | Why is this NA, does France do not have pitcher? Please provide input | Diksha Koul | 2016-09-07 | Vasiliy | No changes in configuration
26 | Pitcher | (2.3) If eDetails is enabled (pfizer_hcp2_edetail pfizer_hcp2_edetail_pitcher pfizer_hcp2_edetail_perms) verify that platform is 2.3.3 or greater |  | 5 |  | N/A | Does France HCp do not have eDetail. | Diksha Koul | 2016-09-07 | Vasiliy | No changes in configuration
27 | Branding | (2.3.3) Remove pfizer_pro_product_branding module if it exists ( this feature now incorporated into 2.3.3) |  | 5 |  | N/A |  | Diksha Koul | 2016-09-07 | Vasiliy | Not present
28 | Branding | Has custom branding S3 host been configured for each of the environments(Dev/Stg/Prod) in Local.settings.php $conf[pfizer_pro_s3_bucket]? |  | 5 |  |  | Please provide input | Manish Goyal
29 | Content | Verify "Full HTML with Scripts" Text Format for Brightcove. /admin/config/content/formats |  | 5 |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
30 | Performance | Confirm with BT Support that Acquia has enabled "Varnish through SSL" option. |  | 5 |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy | Currently enabled in Prod
31 | Janrain | If integrating with 3rd party validation, insure production domain name has been whitelisted with Janrain prior to launch, Email (DL-BT-DIGITALMARKETING@pfizer.com) to confirm. | GRV | 5 |  | N/A | Why is this NA, please provide the details. | Diksha Koul | 2016-09-07 | Vasiliy | The site is in Production. Nothing has changed in this area
32 | Content | Has the portal "demo" content been removed and un-published from the site and Brands feed? |  | 5 |  | Yes |  | Content Team
33 | Migration | Do we have PMI (PfizerMedInfo) built for the market in question? And if so, is there interconnectivity of the authentication solution in place? | - | 5 |  |  | Please provide input | BT
34 | Migration | If preexisting site, has Pfizer Connect user data migration been completed for this market to the new GRV solution? | GRV | 5 |  |  | Please provide input | BT
35 | SDLC | Has the SDLC Deployment Document been completed for Code Changes (must be sent with MTP documentation prior to the deployment)? | MTP | Min. 3 days prior to MTP |  |  | Please provide input | Manish Goyal
36 | SDLC | Has the SDLC Deployment Document been completed for Content Changes (must be sent with MTP documentation prior to the deployment)? | MTP | Min. 3 days prior to MTP |  |  | Please provide input | Content Team
37 | SDLC | Has the business unit sent approval email? Include approval email in Deployment Plan documentation. | MTP | Min. 3 days prior to MTP |  |  | Please provide input | BT
38 | SDLC | Have you scheduled the MTP with the Support Team (email to DL-BT at least 3 days in advance of deployment date)? | MTP | Min. 3 days prior to MTP |  | N/A |  | Diksha Koul
39 | SDLC | Has the BT Solutions Center sent approval email? Include approval email in Deployment Plan documentation. | MTP | Min. 3 days prior to MTP |  |  | Please provide input | BT
40 | Janrain | Confirm GRV configuration information for Production is included in the Deployment Plan. | GRV | Min. 3 days prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
41 | Custom | Create changelog.txt in the GitHub directory and fill in details of what has been customised whilst deploying this Portal. |  | Prior to MTP |  |  | Please provide input | Manish Goyal
42 | Janrain | Delete all GRV test accounts, disable all non-essential Drupal accounts |  | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy | “users” and all related to users tables will be skipped during MTP
43 | Custom | pfizer_pro_product_branding - If used verify that Brands.css and Brands.js files are moved into production S3 bucket - https://github.com/pfizer/pfizerpro-global-s3 |  | Prior to MTP |  | N/A | Please provide input | Diksha Koul | 2016-09-07 | Vasiliy | pfizer_pro_branding - is not present anymore the internal pfizer_products is handling the js/css
44 | Kuluvalley | If KuluValley is enabled have the Webinar email settings been configured? /admin/config/hcp/webinar |  | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
45 | Brightcove | Has the BrightCove configuration for Production been confirmed and added to local.settings.php? | BrightCove | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
46 | Language | Has the site been translated into market's language(s). Are Language settings correctly set to support single or multiple languages. | Deploy | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
47 | SDLC | Have you read & followed the Pfizer technical standard guides: Drupal Custom | Deploy | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
48 | SDLC | Have you read & followed the Pfizer technical standard guides: Drupal Custom | Deploy | Prior to MTP |  |  |  | Manish Goyal
49 | Security | Has the security test been completed and approved? Include approval email in Deployment Plan documentation. | Security | Prior to MTP |  |  | Please provide an input | Manish Goyal
50 | Security | Has the security test been completed and approved? Include approval email in Deployment Plan documentation. | Security | Prior to MTP |  |  |  | Manish Goyal
51 | Security | Have you completed the securepages configuration? Have you confirme that /user and /admin pages are using SSL. | Deploy | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy | We didn’t configure any since market is live
52 | Security | secure cookies have been enabled? $conf['https'] = FALSE; | Deploy | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
53 | Content | Have you removed and/or updated the favicon.ico | Omniture / IM | Prior to MTP |  |  | Please provide an input | Content Team
54 | Security | Ensure that anonymous users do not have elevated permissions. Make sure anonymous user does not have permission to create account on sites (unless its business requirement). admin/config/people/accounts | Deploy | Prior to MTP |  |  | Please provide an input | Manish Goyal
55 | Security | Have you verified configuration for new Drupal pages. Make sure anonymous users DO NOT have admin rights to view unpublished, create, or update nodes/pages. /admin/people/permissions | Deploy | Prior to MTP |  |  | Please provide an input | Manish Goyal
56 | Performance | Has Drupal and Varnish cache been enable on site? Please refer to Improving website performance: https://docs.digitalpfizer.com/drupal-custom-development/improving-website-performance | Deploy | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
57 | Metrics | Confirm Omniture / Web Standards module is enabled (pfizer_webstandards_hcp2) and configurations are in local.settings.php. Review the actual suite in SiteCatalyst to see if the events are indeed firing correctly and the correct suite name is being used on dev and prod. Ensure any dev settings have been removed or deprecated so they do not impact production. Check ALL specific events, e.g. registration, event registration etc. | Omniture / IM | Prior to MTP AND Day of MTP |  |  | Please provide an input | Manish Goyal
58 | Performance | Have routes for vanity urls been created, including non-www url to the primary domain? (Platform team will procure SSL for only for primary domain.) Redirect for both http and https. apache_custom.conf | DNS | Prior to MTP |  |  | What are the vanity urs for france ? | Manish Goyal
59 | Security | Have reoutes been created to route user/login, user/password, and user/register to /login? |  | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
60 | Content | Is the Web service connectivity (ie: Brands feed) configured as per the required environments in Local.settings.php (stage/production) ? | - | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy | Did not touch it
61 | Security | Verify that Devel and Backup & Migrate have been disabled on production |  | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
62 | Content | Verify that Deploy is enabled/disabled per market requirements. | DNS | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
63 | Metrics | Do you need a specific page (other than the home page) to be added to the support monitoring solution? | Support | Min. 3 days prior to MTP |  |  | Please provide input | BT
64 | Custom | Confirm Behat tests completed and passed. | - | N/A |  |  | Please provide input | Manish Goyal
65 | SDLC | Confirm production deployment Git tag. | Deploy | Day of MTP |  |  |  | Diksha Koul
66 | SDLC | Has the approved site been pushed to stg for MTP? |  | Min. 3 days prior to MTP |  |  |  | Diksha Koul
67 | General | Are amazon S3 files(CSS/JS/Assets) moved from Dev to Stg bucket? |  |  |  | N/A |  | Diksha Koul | 2016-09-07 | Vasiliy | No changes have been made in files hosted on Amazon S3
68 | SDLC | Have you completed the KT Checklist and documentation? |  | N/A |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
69 | SDLC | Have you scheduled the KT Meeting? |  | N/A |  |  |  | Diksha Koul
70 | Janrain | IF moving GRV into production for the first time, advise Chris L so that he can enable production GRV Admin Tool. | SSL | Day of MTP |  | N/A |  | Diksha Koul | 2016-09-07 | Vasiliy | Not the first time
71 | Content | Prior prod launch check with Oleg to ask if the prod domains were whitelisted for fontdeck.com |  | Prior to MTP |  | N/A |  | Diksha Koul | 2016-09-07 | Vasiliy | No longer required (fonts are included in 2.7.7 theme)
72 | Acquia | Make sure $_ENV is used instead of $_SERVER in local.settings.php |  | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
73 | Security | Make sure your deployment instruction have "Allow login" set to "YES" since this is a requirement for GRV |  | Day of MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
74 | Performance | Is Memcache configured correctly within local.settings.php? |  | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
75 | Performance | Is the memory_limit set to at least 512 in local.setting.php for all environments |  | Prior to MTP |  | Yes |  | Diksha Koul | 2016-09-07 | Vasiliy
76 | GRV | GRV Admin Tool Onboarding for a country business person, who will be managing GRV users for the country |  | Prior to MTP |  |  | Please provide input | BT
77 | General | Anonymous user shouldn’t see the home and product pages |  |  |  |  | Please provide input if this is a requirement for France? | Manish Goyal

## BT Questions
BT need to respond to below queries before Go Live
Verify the domain name is secured and using a standard Pfizer name server. http://www.whois.com or other in-market service
Do we have PMI (PfizerMedInfo) built for the market in question? And if so, is there interconnectivity of the authentication solution in place?
If preexisting site, has Pfizer Connect user data migration been completed for this market to the new GRV solution?
Has the business unit sent approval email? Include approval email in Deployment Plan documentation.
Has the BT Solutions Center sent approval email? Include approval email in Deployment Plan documentation.
Do you need a specific page (other than the home page) to be added to the support monitoring solution?
GRV Admin Tool Onboarding for a country business person, who will be managing GRV users for the country

## L3 Team Questions
L3 need to respond to below queries before MTP
On which enviroemnt is the latest code residing
Have any custom code been written by L3 support team? Is code reviewed?
Has L3 Team run the Coder Report on custom modules/code and upload these reports to the deployment documents folder?
Has custom branding S3 host been configured for each of the environments(Dev/Stg/Prod) in Local.settings.php $conf[pfizer_pro_s3_bucket]?
Has the SDLC Deployment Document been completed for Code Changes (must be sent with MTP documentation prior to the deployment)?
Create changelog.txt in the GitHub directory and fill in details of what has been customised whilst deploying this Portal.
Have you read & followed the Pfizer technical standard guides: Drupal Custom
Has the security test been completed and approved? Include approval email in Deployment Plan documentation.
Ensure that anonymous users do not have elevated permissions. Make sure anonymous user does not have permission to create account on sites (unless its business requirement). admin/config/people/accounts
Have you verified configuration for new Drupal pages. Make sure anonymous users DO NOT have admin rights to view unpublished, create, or update nodes/pages. /admin/people/permissions
Confirm Omniture / Web Standards module is enabled (pfizer_webstandards_hcp2) and configurations are in local.settings.php. Review the actual suite in SiteCatalyst to see if the events are indeed firing correctly and the correct suite name is being used on dev and prod. Ensure any dev settings have been removed or deprecated so they do not impact production. Check ALL specific events, e.g. registration, event registration etc.
Have routes for vanity urls been created, including non-www url to the primary domain? (Platform team will procure SSL for only for primary domain.) Redirect for both http and https. apache_custom.conf
Confirm Behat tests completed and passed.
Anonymous user shouldn’t see the home and product pages