## Sheet1
Checkpoint | Verification Point | Date Completion | Status | Comment
Platform version | Check if the platform version is at latest stable release |  | Fail | Platform must be reverted to 2.7.5
Coder Report / Code review | Check if coder report is present and if there is any critical warning in coder report. Coder report should be in txt format. | 2016-09-09 | Pass
Deployment checklist / Verification Checklist | Check if the assets provided has deployment checklist and review if deployment checklist is complete | 2016-09-09 | Fail | Deployment checklist in incomplete
QA Document | Check of QA sheet is provided as a part of KT docs | 2016-09-09 | Fail | QA document missing
Epic Ticket |  | 2016-09-09 | Fail | 1. There is no clarity on features of 2.7 being added. 2. There are JIRA ticket open - PUVTMM-272, PUVTMM-283, PUVTMM-324, PUVTMM-340, PUVTMM-383
Security Scan Report | generally this is not present at the time of KT, but do mention this to Upgrade PM POC (Pavan / Oleg) | 2016-09-09 | Pass | Report status is pass but 4 Low severity and one existing issues, are present in the report.
PI Tool Report | Chec in pi.digitalpfizer.com if PI platform check if Pass and Fail | 2016-09-09 | Pass | Please revert it back on Platform version 2.7.5.
UAT Signoff | Based on the date provided in upgrade calander | 2016-09-09 | Pending
SDLC Document | Check if the SDLC document is present and all details are verified | 2016-09-09 | Fail | 1. Please confirm if SR145616 is correct. 2. As per Row #7, platform version of upgraded environment should be 2.7.6 but it should be at 2.7.5 as higher versions are not stable at the moment. 3. Row # 9 , please mention the change type correctky 4. Please verify if CMDB id is correct and compliance status is confirmed by solution center owner. 5. Under deployment instructions, please mention the instructions for moving Amazon S3 buckets for CSS/JS and brand json files from stage to prod. 6. Please confirm the Business Owner, BT representative and BT Project Manager
Omniture Report |  | 2016-09-09 | Fail | Omniture report is not present in deployment document.
Market Customization Report | Check for the market level customization done in the portal if any | 2016-09-09 | Fail | Market customization details are not provided in mail or in epic ticket.
Dev5 Admin Creds | Check if you are provided with Dev5 admin credentials | 2016-09-09 | Pass
Content Team Approval | Get the approval from content team if a live site is getting upgraded. | 2016-09-09 | Pending
Dev3 upgrade plan | In case a live site is getting upgraded , please get the clear plan of action for upgradation of Dev3 instance. | 2016-09-09 | Pass
Code and content freeze | In case of live markets, please get the timeline for code and content freeze dates and inform the regional market lead | 2016-09-09 | Fail | Please confirm the content freeze period
Get the list of Self Service Users from Pavan/Oleg | Get the list of Sefl Service users from upgrade PM poc and provision the users on dev and dev2 and dev3 environments. | 2016-09-09 | Fail | Get the SS users list
Get the list of Content editors for the portal from Pavan/Oleg | Get the list of content editors and add them to Dev3 environment | 2016-09-09 | Fail | Get the SS users list

## Sheet2
QA Checklist HCP Portal France v2.6 Issues Found
Below features should be disabled as per QA checklist. HCP: Webinar- All HCP2: Web Standards Below features should be enabled as per QA checklist. HCP: Add-this integration HCP: Multiple Brand URLs HCP Deep linking HCP: ePermissions Pfizer HCP2 Marketing HCP: Ratings HCP: Webform Pfizer HCP2: Velaro Chat In Pfizer HCP - all not found
Below modules are disabled: -SiteCatalyst -Pfizer Web Standards
SiteCatalist settings are set for netherland i.e., http://pfizer.112.2o7.net/b/ss/pfizerhcpportalnetherlandsdev/1/JS-1.2.2--NS/0.