## Sheet1
# | Item | Done? | Action Item | Date Complete | Confirmed By | Notes
1 | Have we received Deployment Kit(MTP Excel, SDLC, Security,Security Approval email, Coder report, Omniture artifacts from FFW Project team. We must receive it in both cases Fresh Launch of site is already soft launched. | Yes | If No, then immediately Drop email to FFW project team( Kim, Nora, Oleg) and ask them to provide MTP Kit, and let requester know that without that information we canot start MTP process.
2 | Is content work Finished? It must be finished 5 days prior to MTP date | Content | If No, it must be finished 5 days prior to MTP, as support needs to move Dev3 to Stage and perform verifications.
3 | Which Environment has latest content? | Content
4 | Is there any support ticket open? If any support ticket is still open, does it require Security Scan? | Security | If Yes, then first we need to verify with requester, that if that support ticket is not a showstopper
5 | Which environment has latest code? | Code
6 | Have any custom code been written by any Project Team? If Yes, Is it complete? | Code | If No, then it must be finished 5 days prior to MTP
7 | Is there a clean security report and coder provided by Project Team? | Security | If No, then MTP cant take place, as this is a MUST have thing for MTP. We need to inform requester about its impact on MTP date.
8 | On which environment that code is sitting? | Code | NA
9 | Is there any custom GRV work done on this portal? If Yes, is that work completed? Get Details of Project team and know where the work is sitting. | GRV | If No, it must be finished 5 days prior to MTP.
10 | Has a Compliance Risk Profile (CRP) & a CMDB record been generated? https://docs.digitalpfizer.com/sdlc-documentation/cmdb-iprm | Security | If No, Need to highlight to Project team and ask them to get it done.
11 | Verify the domain name is secured and using a standard Pfizer name server. Check on this link http://www.iana.org/domains/root/db | DNS | If No then Inform BT. This must be obtained and must be with BT Support team in order to do DNS cutover. Confirm with BT Support Team
12 | Is SSL certificate configured for primary domain. (Any page that captures user information needs to be on SSL) | SSL | If No, then inform BT Manager that its SLA is 10-12 days. and raise ticket with BT Support team for it.
13 | Do we have PMI (PfizerMedInfo) built for the market in question? And if so, is there interconnectivity of the authentication solution in place? | GRV | If Yes, we need to inform Dasha Vashchilenko <dasha.vashchilenko@ffwagency.com>; Segal, Ron <Ron.Segal@pfizer.com> about it, As they also need to migrate their data to GRV.
14 | If preexisting site, has Pfizer Connect user data migration been completed for this market to the new GRV solution? | GRV | If Yes, then check with 'Christi Jones' <christi.jones@ffwagency.com> whats the status of Data Migration
15 | Remove all Search index if we are moving database from one env to other. We need to check for Subscriptions with per-environment SolR indexes. Example ticket - https://insight.acquia.com/support/tickets/247716?s=1270091#animated | Config
16 | non www URL redirect to www URL, must be mentioned in source/deploy/apache_custom.conf file | Config